## Overview
| Team | Andrei | Bach | Brandon | Cody | Peter | Zack
Total Task List Hours | 25.75 | 6.75 | 3 | 2.5 | 5.5 | 1.5 | 6.5
Total Task List Costs | 2575 | 675 | 300 | 250 | 550 | 150 | 650
Total Weekly Meeting Hours | 9.25
Total Weekly Meeting Costs | 5375
Total Hours | 35
Total Costs | 7950

## Burn Report
| Per Person | [10 empty] | Individual Costs | [7 empty] | Individual Time Spent
Date | Task | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost | Unit Cost | 100 |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack
2018-02-06 | Meeting Planning | 0.5 | 1 | [5 empty] | 50 |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0
2018-02-13 | Meeting Planning | 0.5 | 1 | [5 empty] | 50 |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0
2018-02-22 | Derive Requirements for Motor | 2 |  | 1 | 1 | 1 |  |  | 600 |  |  |  | 0 | 200 | 200 | 200 | 0 | 0 |  |  | 0 | 2 | 2 | 2 | 0 | 0
2018-02-22 | Derive Requirements for Motor | 1 |  | 1 |  |  |  |  | 100 |  |  |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0
2018-02-22 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  | 1 | 200 |  |  |  | 0 | 0 | 0 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 1 | 0 | 1
2018-02-24 | Block diagram for whole system | 1 |  |  |  |  | 1 |  | 100 |  |  |  | 0 | 0 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0
2018-02-26 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100 |  |  |  | 0 | 0 | 0 | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0
2018-02-27 | Derive Requirements for sensors | 0.5 |  |  |  |  | 1 |  | 50 |  |  |  | 0 | 0 | 0 | 0 | 50 | 0 |  |  | 0 | 0 | 0 | 0 | 0.5 | 0
2018-02-28 | Create a block diagram for PWM | 0.5 |  |  | 1 |  |  |  | 50 |  |  |  | 0 | 0 | 50 | 0 | 0 | 0 |  |  | 0 | 0 | 0.5 | 0 | 0 | 0
2018-02-28 | Python Motor idea implementation | 0.5 |  |  |  | 1 |  |  | 50 |  |  |  | 0 | 0 | 0 | 50 | 0 | 0 |  |  | 0 | 0 | 0 | 0.5 | 0 | 0
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | [5 empty] | 1 | 50 |  |  |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5
2018-03-01 | Finish up task list, updated burn list, and started gantt | 1.5 | 1 | [5 empty] | 150 |  |  |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0
2018-03-01 | Python Sensor idea implementation | 1 | [5 empty] | 1 | 100 |  |  |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1
2018-03-05 | Explore opencv object detection | 1 | [5 empty] | 1 | 100 |  |  |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1
2018-03-06 | Create and train Haar cascades for various ‘brick’ faces | 2 | [5 empty] | 1 | 200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 2
2018-03-06 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100 |  |  |  | 0 | 0 | 0 | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0
2018-03-06 | Created initial revision of pre-pdr gantt | 1 | 1 |  |  |  |  | 1 | 200 |  |  |  | 100 | 0 | 0 | 0 | 0 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 1
2018-03-07 | Retrain cascades with new samples – shell script automation | 0.5 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
2018-03-07 | Worked on Gantt and organizing files | 1 | 1 | [5 empty] | 100 |  |  |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-13 | Organized Files in folders | 0.25 | 1 | [5 empty] | 25 |  |  |  | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0.25 | 0 | 0 | 0 | 0 | 0
2018-03-14 | Further Organized and Updated Gantt | 1 | 1 | [5 empty] | 100 |  |  |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-15 | Worked on Powerpoint and Gantt. Communicated with team | 1 | 1 | [5 empty] | 100 |  |  |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Cost | 25.75 | 675 | 300 | 250 | 550 | 150 | 650 | 2575
|  | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Total | 675 | 300 | 250 | 550 | 150 | 650 | 2575 |  | 6.75 | 3 | 2.5 | 5.5 | 1.5 | 6.5 | 25.75

## Weekly Meeting Costs
Date | Hours | Andrei | Bach | Brandon | Cody | Peter | Zach | Task Cost | Notes | Unit Cost | 100
2018-02-01 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-06 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-08 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-13 | 0.75 | 1 | 0 | 1 | 1 | 1 | 1 | 375
2018-02-20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600 | Overview + Subsystems
2018-02-22 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 500 | Motor Requirements
2018-02-27 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 900 | Sensor Requirements
2018-03-01 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1200 | Powerpoint, encoders,
2018-03-05 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300 | PDR discussion
2018-03-06 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600 | Project Plan Review & obj for spring break
2018-03-08 | [7 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
| 9.25 | [6 empty] | 5375 | Total