## Project Planner
New folder Project Planner
2018-03-14 21:29 | [5 empty] | Period Highlight: | 14 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | USER | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS | [30 empty] | April
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
System |  | 1 | 13 | 0 | 0 | 0%
Create overview system design | Team | 1 | 6 | 1 | 0 | 0%
Block diagram for whole system | Team | 1 | 8 | 0 | 0 | 0%
System Requirements | Bach & Team | 1 | 8 | 0 | 0 | 0%
Mechanical Drawings | Bach | 6 | 13 | 0 | 0 | 0%
Sensor Trade Study* (choice of sensors) | Team & Bach | 1 | 6 | 0 | 0 | 0%
Create functional test* |  | 13 | 5 | 0 | 0 | 0%
VHDL - PWM (Duty Cycle) |  | 13 | 5 | 0 | 0 | 0%
Python - Encoders & PWM | Cody | 13 | 5
C - Polling & Interrupts |  | 13 | 0 | 0 | 0 | 0%
VHDL - Ultrasonic Sensors |  | 13 | 0 | 0 | 0 | 0%
Develop Tech Memo* | Team | 13 | 6 | 0 | 0 | 0%
PWM? |  | 13 | 6 | 0 | 0 | 0%
Python - TBD |  | 13 | 6
Rover? | Andrei | 13 | 6 | 0 | 0 | 0%
Define Technical Deliverables* | Andrei | 8 | 13 | 0 | 0 | 0%
VHDL |  | 1 | 8 | 0 | 0 | 0%
Derive Requirements for VHDL | Bach | 1 | 6 | 0 | 0 | 0%
Create a block diagram for PWM | Brandon & Peter | 1 | 6 | 6 | 2 | 100%
Design VHDL\AXI block for PWM | Brandon & Peter | 1 | 8 | 6 | 2 | 100%
Design VHDL\AXI block for sonic sensors | Brandon & Peter | 1 | 8 | 6 | 2 | 100%
Design block for sonic sensors
Register Mapping | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Python |  | 1 | 8 | 0 | 0 | 0%
Figure out software requirements | Cody & Zack & Bach | 1 | 8 | 4 | 3 | 100%
Design GUI and brainstorm ideas for functionality | Cody & Zack | 1 | 8 | 0 | 0 | 0%
Plan what types of functions for movement | Cody & Zack | 1 | 6 | 1 | 3 | 100%
Plan how to process encoders | Cody & Zack | 1 | 8 | 1 | 3 | 50%
Python IMU functions (gyro) | Cody & Zack | 1 | 6 | 0 | 0 | 0%
Plan calibration implementation | Cody & Zack | 1 | 6 | 1 | 2 | 100%
C Development |  | 1 | 8 | 0 | 0 | 0%
Register Mapping | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Design a process on Polling & Interrupt | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Plan function names for the drivers | Brandon & Peter | 1 | 6 | 1 | 6 | 100%
Hardware |  | 1 | 8 | 0 | 0 | 0%
Derive Requirements for Motor | Bach | 1 | 8 | 0 | 4 | 0%
Derive Requirements for IMU | Bach | 6 | 8 | 0 | 0 | 0%
Derive Requirements for LED | Bach | 6 | 8 | 0 | 0 | 0%
Derive Requirements for Ultrasonic Sensors | Bach | 1 | 6 | 1 | 4 | 100%
Derive Requirements for Audio Speaker* | Andrei & Bach | 6 | 2 | 0 | 0 | 0%
Derive Requirements for Cameras | Bach | 8
Plan a way to calibrate rover | Cody & Zack | 1 | 8 | 1 | 0 | 50%
Project Management |  | 1 | 22 | 0 | 0 | 0%
Create logging sheets for easy reports | Andrei | 1 | 6 | 1 | 6 | 100%
Scheduling pre PDR | Andrei | 1 | 8 | 1 | 0 | 75%
Scheduling post PDR | Andrei | 8 | 2 | 0 | 0 | 0%
Create Powerpoint | Andrei & Cody | 4 | 14 | 6 | 0 | 1%
Practice PDR | Team | 18 | 5 | 0 | 0 | 0%
PDR | Team | 22 | 1 | 22 | 1 | 0%
VHDL |  | 22 | 0 | 0 | 0 | 0%
Create AXI on Vivado |  | 22 | 0 | 0 | 0 | 0%
Write VHDL for sonic sensors | B & P | 22 | 0 | 0 | 0 | 0%
Calibration - VHDL side | B & P | 22 | 0 | 0 | 0 | 0%
Implement PWM final design | B & P | 22 | 0 | 0 | 0 | 0%
Python |  | 22 | 0 | 0 | 0 | 0%
Make turning smart with gyro | Cody & Zack | 0 | 0 | 0 | 0 | 0%
C Development |  | 22 | 0 | 0 | 0 | 0%
Write code to read sonic sensors | Brandon & Peter | 0 | 0 | 0 | 0 | 0%
Code up sonic sensors calibration | Brandon & Peter | 0 | 0 | 0 | 0 | 0%