## Burn Report
| Per Person | [8 empty] | Individual Costs | [7 empty] | Individual Time Spent
Date | Task | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack
2018-02-04 | [Ignore] For Chart Formatting | 0 | [6 empty] | 0 | [16 empty] | Pre PDR Cost | 1275 | 1450 | 250 | 750 | 550 | 850
2018-02-06 | Meeting Planning | 0.5 | 1 | [5 empty] | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Post PDR Cost | 650 | 0 | 0 | 50 | 100 | 750
2018-02-13 | Meeting Planning | 0.5 | 1 | [5 empty] | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0
2018-02-22 | Derive Requirements for Motor | 2 |  | 1 | 1 | 1 |  |  | 600 |  | 0 | 200 | 200 | 200 | 0 | 0 |  |  | 0 | 2 | 2 | 2 | 0 | 0 |  | Pre PDR Hours | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5
2018-02-22 | Derive Requirements for Motor | 1 |  | 1 |  |  |  |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | Post PDR Hours | 6.5 | 0 | 0 | 0.5 | 1 | 7.5
2018-02-22 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  | 1 | 200 |  | 0 | 0 | 0 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 1 | 0 | 1
2018-02-22 | Gather hardware manuals along with examples for hardware implementations | 2 |  | 1 |  |  |  |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | Total Cost | 1925 | 1450 | 250 | 800 | 650 | 1600
2018-02-24 | Block diagram for whole system | 1 |  |  |  |  | 1 |  | 100 |  | 0 | 0 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 |  | Total Hours | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 16
2018-02-26 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100 |  | 0 | 0 | 0 | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0
2018-02-26 | Came up with requirements for system and modules | 1 |  | 1 |  |  |  |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0
2018-02-27 | Derive Requirements for sensors | 0.5 |  | 1 |  |  | 1 |  | 100 |  | 0 | 50 | 0 | 0 | 50 | 0 |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0
2018-02-27 | Wrote a summary and requirement report for ultrasonic sensors | 2 |  | 1 |  |  |  |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0 | 0 | 0 | 0
2018-02-28 | Create a block diagram for PWM | 0.5 |  |  | 1 |  |  |  | 50 |  | 0 | 0 | 50 | 0 | 0 | 0 |  |  | 0 | 0 | 0.5 | 0 | 0 | 0
2018-02-28 | Python Motor idea implementation | 0.5 |  |  |  | 1 |  |  | 50 |  | 0 | 0 | 0 | 50 | 0 | 0 |  |  | 0 | 0 | 0 | 0.5 | 0 | 0
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5
2018-03-01 | Finish up task list, updated burn list, and started gantt | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0
2018-03-01 | Python Sensor idea implementation | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1
2018-03-05 | Explore opencv object detection | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1
2018-03-06 | Create and train Haar cascades for various ‘brick’ faces | 2 | [5 empty] | 1 | 200 |  | 0 | 0 | 0 | 0 | 0 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 2
2018-03-06 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100 |  | 0 | 0 | 0 | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0
2018-03-06 | Created initial revision of pre-pdr gantt | 1 | 1 |  |  |  |  | 1 | 200 |  | 100 | 0 | 0 | 0 | 0 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 1
2018-03-07 | Retrain cascades with new samples – shell script automation | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5
2018-03-07 | Worked on Gantt and organizing files | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-08 | Came up with test plan for system and modules | 1 |  | 1 |  |  |  |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0
2018-03-13 | Design GUI and brainstorm ideas for functionality | 2 |  |  |  | 1 |  |  | 200 |  | 0 | 0 | 0 | 200 | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 0 | 0
2018-03-13 | Organized Files in folders | 0.25 | 1 | [5 empty] | 25 |  | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0.25 | 0 | 0 | 0 | 0 | 0
2018-03-14 | Further Organized and Updated Gantt | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-14 | Researched OpenCV functionality with python | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5
2018-03-15 | Worked on Powerpoint and Gantt. Communicated with team | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-17 | Brainstormed project's application and purpose | 0.5 | 1 | [5 empty] | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0
2018-03-18 | Created Powerpoint skeleton and updated Gantt. | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-20 | Designed VHDL block dragrams for sensor modules. | 1.5 |  |  |  |  | 1 |  | 150 |  | 0 | 0 | 0 | 0 | 150 | 0 |  |  | 0 | 0 | 0 | 0 | 1.5 | 0
2018-03-20 | Wrote VHDL for sensor modules. | 2.5 |  |  |  |  | 1 |  | 250 |  | 0 | 0 | 0 | 0 | 250 | 0 |  |  | 0 | 0 | 0 | 0 | 2.5 | 0
2018-03-20 | Added OpenCV and python module to PDR | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1
2018-03-21 | Cleaned up Burn Report and added intro into slides | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0
2018-03-21 | Drove to fire station and interviewed with firemen to get ideas on how to help them | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-21 | Added requirements for the system as a whole and for each subsystem to PDR | 3 |  | 1 |  |  |  |  | 300 |  | 0 | 300 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 0 | 0 | 0 | 0
2018-03-21 | Added hardware overview and test plan to PDR | 2 |  | 1 |  |  |  |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0 | 0 | 0 | 0
2018-03-21 | Worked on PP | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-03-22 | Finalized PP | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 | Total PDR Costs |  | 1 | 0 | 0 | 0 | 0 | 0 | Total PDR hours
2018-03-24 | Researched localization and other algorithms | 3 | [5 empty] | 1 | 300 |  | 0 | 0 | 0 | 0 | 0 | 300 | 5125 |  | 0 | 0 | 0 | 0 | 0 | 3 | 51.25
2018-03-26 | Created Individual Gantt Charts for each team member | 2 | 1 | [5 empty] | 200 |  | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | 0 | 0 | 0 | 0 | 0
2018-03-27 | Created basic Memory Access Unit tests in Python and C | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5
2018-03-28 | Added more metrics to our Planner and combined reports/created dashboard for flexibility | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-04-02 | Messing around with dashboard and charts | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0
2018-04-04 | Experimenting creation of time card | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-04-06 | Remapped Python GUI memory and verified functionality | 0.5 |  |  |  | 1 |  |  | 50 |  | 0 | 0 | 0 | 50 | 0 | 0 |  |  | 0 | 0 | 0 | 0.5 | 0 | 0
2018-04-09 | Wrote functional test for Professor’s system | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1
2018-04-09 | Researched OpenCV and developed camera calibration script | 1.5 | [5 empty] | 1 | 150 |  | 0 | 0 | 0 | 0 | 0 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 1.5
2018-04-10 | Cleaned up Metrics, polished up burn reports & discarding time card | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0
2018-04-10 | Wrote VHDL for encoder reader and counter. | 1 |  |  |  |  | 1 |  | 100 |  | 0 | 0 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0
2018-04-11 | Familiarize IMU and wrote script integrating turn and IMU | 1.5 | [5 empty] | 1 | 150 |  | 0 | 0 | 0 | 0 | 0 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 1.5
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Total CDR Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | Total CDR Costs
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1550 |  | 0 | 0 | 0 | 0 | 0 | 0 | 15.5
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Total | 60.25 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 16 | 6675 | Total | 1925 | 1450 | 250 | 800 | 650 | 1600 | 6675 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 16 | 66.75
|  | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost