## Burn Report
| Per Person | [8 empty] | Individual Costs | [7 empty] | Individual Time Spent | [14 empty] | Individual Costs | [7 empty] | Individual Time Spent | [7 empty] | Individual Costs
Date | Task | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  | Andrei | Bach | Brandon | Cody | Peter | Zack | Team |  | Andrei | Bach | Brandon | Cody | Peter | Zack | Team |  | Andrei | Bach | Brandon | Cody | Peter | Zack | Team |  | Individual Costs | [7 empty] | Individual Time Spent
2018-02-04 | [Ignore] For Chart Formatting | 0 | [6 empty] | 0 | [16 empty] | Pre PDR Cost | 1275 | 1450 | 250 | 750 | 550 | 850 | [26 empty] | Andrei | Bach | Brandon | Cody | Peter | Zack | Team |  | Andrei | Bach | Brandon | Cody | Peter | Zack
2018-02-06 | Meeting Planning | 0.5 | 1 | [5 empty] | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Post PDR Cost | 800 | 0 | 400 | 250 | 350 | 1600 |  | 50 | 0 | 0 | 0 | 0 | 0 | 50 |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 50 | 0 | 0 | 0 | 0 | 0 | 3400 | 2018-02-01 |  | 50 | 50 | 50 | 50 | 50 | 50 | 300 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
2018-02-13 | Meeting Planning | 0.5 | 1 | [5 empty] | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 100 | 0 | 0 | 0 | 0 | 0 | 100 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 50 | 0 | 0 | 0 | 0 | 0 | 3400 | 2018-02-06 |  | 100 | 100 | 100 | 100 | 100 | 100 | 900 |  | 1 | 1 | 1 | 1 | 1 | 1
2018-02-22 | Derive Requirements for Motor | 2 |  | 1 | 1 | 1 |  |  | 600 |  | 0 | 200 | 200 | 200 | 0 | 0 |  |  | 0 | 2 | 2 | 2 | 0 | 0 |  | Pre PDR Hours | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 |  | 100 | 200 | 200 | 200 | 0 | 0 | 700 |  | 1 | 2 | 2 | 2 | 0 | 0 | 7 | [8 empty] | 2018-02-08 |  | 150 | 150 | 150 | 150 | 150 | 150 | 1800 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2018-02-22 | Derive Requirements for Motor | 1 |  | 1 |  |  |  |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | Post PDR Hours | 6.5 | 0 | 2 | 2.5 | 1 | 16 |  | 100 | 300 | 200 | 200 | 0 | 0 | 800 |  | 1 | 3 | 2 | 2 | 0 | 0 | 8 | [8 empty] | 2018-02-13 |  | 225 | 150 | 225 | 225 | 225 | 225 | 3075 |  | 2.25 | 1.5 | 2.25 | 2.25 | 2.25 | 2.25
2018-02-22 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  | 1 | 200 |  | 0 | 0 | 0 | 100 | 0 | 100 |  |  | 0 | 0 | 0 | 1 | 0 | 1 | [9 empty] | 100 | 300 | 200 | 300 | 0 | 100 | 1000 |  | 1 | 3 | 2 | 3 | 0 | 1 | 10 | [8 empty] | 2018-02-20 |  | 325 | 250 | 325 | 325 | 325 | 325 | 4950 |  | 3.25 | 2.5 | 3.25 | 3.25 | 3.25 | 3.25
2018-02-22 | Gather hardware manuals along with examples for hardware implementations | 2 |  | 1 |  |  |  |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0 | 0 | 0 | 0 |  | Total Cost | 2075 | 1450 | 650 | 1000 | 900 | 2450 |  | 100 | 500 | 200 | 300 | 0 | 100 | 1200 |  | 1 | 5 | 2 | 3 | 0 | 1 | 12 | [8 empty] | 2018-02-22 |  | 325 | 350 | 425 | 425 | 425 | 425 | 7325 |  | 3.25 | 3.5 | 4.25 | 4.25 | 4.25 | 4.25
2018-02-24 | Block diagram for whole system | 1 |  |  |  |  | 1 |  | 100 |  | 0 | 0 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 |  | Total Hours | 19.25 | 14.5 | 4.5 | 10 | 6.5 | 24.5 |  | 100 | 500 | 200 | 300 | 100 | 100 | 1300 |  | 1 | 5 | 2 | 3 | 1 | 1 | 13 | [8 empty] | 2018-02-27 |  | 475 | 500 | 575 | 575 | 575 | 575 | 10600 |  | 4.75 | 5 | 5.75 | 5.75 | 5.75 | 5.75
2018-02-26 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100 |  | 0 | 0 | 0 | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [9 empty] | 100 | 500 | 200 | 400 | 100 | 100 | 1400 |  | 1 | 5 | 2 | 4 | 1 | 1 | 14 | [8 empty] | 2018-03-01 |  | 675 | 700 | 775 | 775 | 775 | 775 | 15075 |  | 6.75 | 7 | 7.75 | 7.75 | 7.75 | 7.75
2018-02-26 | Came up with requirements for system and modules | 1 |  | 1 |  |  |  |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 100 | 600 | 200 | 400 | 100 | 100 | 1500 |  | 1 | 6 | 2 | 4 | 1 | 1 | 15 | [8 empty] | 2018-03-05 |  | 725 | 750 | 825 | 825 | 825 | 825 | 19850 |  | 7.25 | 7.5 | 8.25 | 8.25 | 8.25 | 8.25
2018-02-27 | Derive Requirements for sensors | 0.5 |  | 1 |  |  | 1 |  | 100 |  | 0 | 50 | 0 | 0 | 50 | 0 |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0 | [9 empty] | 100 | 650 | 200 | 400 | 150 | 100 | 1600 |  | 1 | 6.5 | 2 | 4 | 1.5 | 1 | 16 | [8 empty] | 2018-03-06 |  | 825 | 850 | 925 | 925 | 925 | 925 | 25225 |  | 8.25 | 8.5 | 9.25 | 9.25 | 9.25 | 9.25
2018-02-27 | Wrote a summary and requirement report for ultrasonic sensors | 2 |  | 1 |  |  |  |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0 | 0 | 0 | 0 | [9 empty] | 100 | 850 | 200 | 400 | 150 | 100 | 1800 |  | 1 | 8.5 | 2 | 4 | 1.5 | 1 | 18 | [8 empty] | 2018-03-08 |  | 875 | 900 | 975 | 975 | 975 | 975 | 30900 |  | 8.75 | 9 | 9.75 | 9.75 | 9.75 | 9.75
2018-02-28 | Create a block diagram for PWM | 0.5 |  |  | 1 |  |  |  | 50 |  | 0 | 0 | 50 | 0 | 0 | 0 |  |  | 0 | 0 | 0.5 | 0 | 0 | 0 | [9 empty] | 100 | 850 | 250 | 400 | 150 | 100 | 1850 |  | 1 | 8.5 | 2.5 | 4 | 1.5 | 1 | 18.5 | [8 empty] | 2018-03-20 |  | 1075 | 900 | 1175 | 1175 | 1175 | 1175 | 37575 |  | 10.75 | 9 | 11.75 | 11.75 | 11.75 | 11.75
2018-02-28 | Python Motor idea implementation | 0.5 |  |  |  | 1 |  |  | 50 |  | 0 | 0 | 0 | 50 | 0 | 0 |  |  | 0 | 0 | 0 | 0.5 | 0 | 0 | [9 empty] | 100 | 850 | 250 | 450 | 150 | 100 | 1900 |  | 1 | 8.5 | 2.5 | 4.5 | 1.5 | 1 | 19 | [8 empty] | 2018-03-27 |  | 1125 | 950 | 1225 | 1225 | 1225 | 1225 | 44550 |  | 11.25 | 9.5 | 12.25 | 12.25 | 12.25 | 12.25
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | [9 empty] | 100 | 850 | 250 | 450 | 150 | 150 | 1950 |  | 1 | 8.5 | 2.5 | 4.5 | 1.5 | 1.5 | 19.5 | [8 empty] | 2018-04-05 |  | 1225 | 1050 | 1325 | 1325 | 1325 | 1325 | 52125 |  | 12.25 | 10.5 | 13.25 | 13.25 | 13.25 | 13.25
2018-03-01 | Finish up task list, updated burn list, and started gantt | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 250 | 850 | 250 | 450 | 150 | 150 | 2100 |  | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 1.5 | 21 | [8 empty] | 2018-04-10 |  | 1300 | 1125 | 1400 | 1400 | 1400 | 1400 | 60150 |  | 13 | 11.25 | 14 | 14 | 14 | 14
2018-03-01 | Python Sensor idea implementation | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 250 | 850 | 250 | 450 | 150 | 250 | 2200 |  | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 2.5 | 22 | [8 empty] | 2018-04-12 |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 68425 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-05 | Explore opencv object detection | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 250 | 850 | 250 | 450 | 150 | 350 | 2300 |  | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 3.5 | 23 | [10 empty] | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 76700 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-06 | Create and train Haar cascades for various ‘brick’ faces | 2 | [5 empty] | 1 | 200 |  | 0 | 0 | 0 | 0 | 0 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | [9 empty] | 250 | 850 | 250 | 450 | 150 | 550 | 2500 |  | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 5.5 | 25 | [10 empty] | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 84975 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-06 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100 |  | 0 | 0 | 0 | 100 | 0 | 0 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | [9 empty] | 250 | 850 | 250 | 550 | 150 | 550 | 2600 |  | 2.5 | 8.5 | 2.5 | 5.5 | 1.5 | 5.5 | 26 | [10 empty] | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 93250 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-06 | Created initial revision of pre-pdr gantt | 1 | 1 |  |  |  |  | 1 | 200 |  | 100 | 0 | 0 | 0 | 0 | 100 |  |  | 1 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 350 | 850 | 250 | 550 | 150 | 650 | 2800 |  | 3.5 | 8.5 | 2.5 | 5.5 | 1.5 | 6.5 | 28 | [10 empty] | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 101525 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-07 | Retrain cascades with new samples – shell script automation | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | [9 empty] | 350 | 850 | 250 | 550 | 150 | 700 | 2850 |  | 3.5 | 8.5 | 2.5 | 5.5 | 1.5 | 7 | 28.5 | [10 empty] | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 109800 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-07 | Worked on Gantt and organizing files | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 450 | 850 | 250 | 550 | 150 | 700 | 2950 |  | 4.5 | 8.5 | 2.5 | 5.5 | 1.5 | 7 | 29.5 | [10 empty] | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 118075 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
2018-03-08 | Came up with test plan for system and modules | 1 |  | 1 |  |  |  |  | 100 |  | 0 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 450 | 950 | 250 | 550 | 150 | 700 | 3050 |  | 4.5 | 9.5 | 2.5 | 5.5 | 1.5 | 7 | 30.5
2018-03-13 | Design GUI and brainstorm ideas for functionality | 2 |  |  |  | 1 |  |  | 200 |  | 0 | 0 | 0 | 200 | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 0 | 0 | [9 empty] | 450 | 950 | 250 | 750 | 150 | 700 | 3250 |  | 4.5 | 9.5 | 2.5 | 7.5 | 1.5 | 7 | 32.5
2018-03-13 | Organized Files in folders | 0.25 | 1 | [5 empty] | 25 |  | 25 | 0 | 0 | 0 | 0 | 0 |  |  | 0.25 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 475 | 950 | 250 | 750 | 150 | 700 | 3275 |  | 4.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7 | 32.75
2018-03-14 | Further Organized and Updated Gantt | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 575 | 950 | 250 | 750 | 150 | 700 | 3375 |  | 5.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7 | 33.75
2018-03-14 | Researched OpenCV functionality with python | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | [9 empty] | 575 | 950 | 250 | 750 | 150 | 750 | 3425 |  | 5.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 34.25
2018-03-15 | Worked on Powerpoint and Gantt. Communicated with team | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 675 | 950 | 250 | 750 | 150 | 750 | 3525 |  | 6.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 35.25
2018-03-17 | Brainstormed project's application and purpose | 0.5 | 1 | [5 empty] | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 725 | 950 | 250 | 750 | 150 | 750 | 3575 |  | 7.25 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 35.75
2018-03-18 | Created Powerpoint skeleton and updated Gantt. | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 825 | 950 | 250 | 750 | 150 | 750 | 3675 |  | 8.25 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 36.75
2018-03-20 | Designed VHDL block dragrams for sensor modules. | 1.5 |  |  |  |  | 1 |  | 150 |  | 0 | 0 | 0 | 0 | 150 | 0 |  |  | 0 | 0 | 0 | 0 | 1.5 | 0 | [9 empty] | 825 | 950 | 250 | 750 | 300 | 750 | 3825 |  | 8.25 | 9.5 | 2.5 | 7.5 | 3 | 7.5 | 38.25
2018-03-20 | Wrote VHDL for sensor modules. | 2.5 |  |  |  |  | 1 |  | 250 |  | 0 | 0 | 0 | 0 | 250 | 0 |  |  | 0 | 0 | 0 | 0 | 2.5 | 0 | [9 empty] | 825 | 950 | 250 | 750 | 550 | 750 | 4075 |  | 8.25 | 9.5 | 2.5 | 7.5 | 5.5 | 7.5 | 40.75
2018-03-20 | Added OpenCV and python module to PDR | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 825 | 950 | 250 | 750 | 550 | 850 | 4175 |  | 8.25 | 9.5 | 2.5 | 7.5 | 5.5 | 8.5 | 41.75
2018-03-21 | Cleaned up Burn Report and added intro into slides | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 975 | 950 | 250 | 750 | 550 | 850 | 4325 |  | 9.75 | 9.5 | 2.5 | 7.5 | 5.5 | 8.5 | 43.25
2018-03-21 | Drove to fire station and interviewed with firemen to get ideas on how to help them | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1075 | 950 | 250 | 750 | 550 | 850 | 4425 |  | 10.75 | 9.5 | 2.5 | 7.5 | 5.5 | 8.5 | 44.25
2018-03-21 | Added requirements for the system as a whole and for each subsystem to PDR | 3 |  | 1 |  |  |  |  | 300 |  | 0 | 300 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 0 | 0 | 0 | 0 | [9 empty] | 1075 | 1250 | 250 | 750 | 550 | 850 | 4725 |  | 10.75 | 12.5 | 2.5 | 7.5 | 5.5 | 8.5 | 47.25
2018-03-21 | Added hardware overview and test plan to PDR | 2 |  | 1 |  |  |  |  | 200 |  | 0 | 200 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 0 | 0 | 0 | 0 | [9 empty] | 1075 | 1450 | 250 | 750 | 550 | 850 | 4925 |  | 10.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 | 49.25
2018-03-21 | Worked on PP | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1175 | 1450 | 250 | 750 | 550 | 850 | 5025 |  | 11.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 | 50.25
2018-03-22 | Finalized PP | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 | Total PDR Costs |  | 1 | 0 | 0 | 0 | 0 | 0 | Total PDR hours | [8 empty] | 1275 | 1450 | 250 | 750 | 550 | 850 | 5125 |  | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 | 51.25
2018-03-24 | Researched localization and other algorithms | 3 | [5 empty] | 1 | 300 |  | 0 | 0 | 0 | 0 | 0 | 300 | 5125 |  | 0 | 0 | 0 | 0 | 0 | 3 | 51.25 | [8 empty] | 1275 | 1450 | 250 | 750 | 550 | 1150 | 5425 |  | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 11.5 | 54.25
2018-03-26 | Created Individual Gantt Charts for each team member | 2 | 1 | [5 empty] | 200 |  | 200 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1475 | 1450 | 250 | 750 | 550 | 1150 | 5625 |  | 14.75 | 14.5 | 2.5 | 7.5 | 5.5 | 11.5 | 56.25
2018-03-27 | Created basic Memory Access Unit tests in Python and C | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | [9 empty] | 1475 | 1450 | 250 | 750 | 550 | 1200 | 5675 |  | 14.75 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 56.75
2018-03-28 | Added more metrics to our Planner and combined reports/created dashboard for flexibility | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1575 | 1450 | 250 | 750 | 550 | 1200 | 5775 |  | 15.75 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 57.75
2018-04-02 | Messing around with dashboard and charts | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1725 | 1450 | 250 | 750 | 550 | 1200 | 5925 |  | 17.25 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 59.25
2018-04-04 | Experimenting creation of time card | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1825 | 1450 | 250 | 750 | 550 | 1200 | 6025 |  | 18.25 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 60.25
2018-04-06 | Remapped Python GUI memory and verified functionality | 0.5 |  |  |  | 1 |  |  | 50 |  | 0 | 0 | 0 | 50 | 0 | 0 |  |  | 0 | 0 | 0 | 0.5 | 0 | 0 | [9 empty] | 1825 | 1450 | 250 | 800 | 550 | 1200 | 6075 |  | 18.25 | 14.5 | 2.5 | 8 | 5.5 | 12 | 60.75
2018-04-09 | Wrote functional test for Professor’s system | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 1825 | 1450 | 250 | 800 | 550 | 1300 | 6175 |  | 18.25 | 14.5 | 2.5 | 8 | 5.5 | 13 | 61.75
2018-04-09 | Researched OpenCV and developed camera calibration script | 1.5 | [5 empty] | 1 | 150 |  | 0 | 0 | 0 | 0 | 0 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 1.5 | [9 empty] | 1825 | 1450 | 250 | 800 | 550 | 1450 | 6325 |  | 18.25 | 14.5 | 2.5 | 8 | 5.5 | 14.5 | 63.25
2018-04-10 | Cleaned up Metrics, polished up burn reports & discarding time card | 1 | 1 | [5 empty] | 100 |  | 100 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1925 | 1450 | 250 | 800 | 550 | 1450 | 6425 |  | 19.25 | 14.5 | 2.5 | 8 | 5.5 | 14.5 | 64.25
2018-04-10 | Wrote VHDL for encoder reader and counter. | 1 |  |  |  |  | 1 |  | 100 |  | 0 | 0 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1450 | 6525 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 14.5 | 65.25
2018-04-11 | Familiarize/tweak IMU and wrote script integrating turn and IMU | 1.5 | [5 empty] | 1 | 150 |  | 0 | 0 | 0 | 0 | 0 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 1.5 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1600 | 6675 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 16 | 66.75
2018-04-14 | Finished sensor python/c unit/integration test | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1700 | 6775 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 17 | 67.75
2018-04-16 | Wrote C memory poking for motors | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1750 | 6825 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 17.5 | 68.25
2018-04-16 | Modularized all components in python with shared object use | 0.5 | [5 empty] | 1 | 50 |  | 0 | 0 | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0.5 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1800 | 6875 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 18 | 68.75
2018-04-16 | Wrote functional test including sensor, imu and motor components | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1900 | 6975 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 19 | 69.75
2018-04-17 | Begun initial work on web interface of rover with straight, left, right, backward, and 360 buttons | 0.75 | [5 empty] | 1 | 75 |  | 0 | 0 | 0 | 0 | 0 | 75 |  |  | 0 | 0 | 0 | 0 | 0 | 0.75 | [9 empty] | 1925 | 1450 | 250 | 800 | 650 | 1975 | 7050 |  | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 19.75 | 70.5
2018-04-17 | GUI - Movement Map | 2 |  |  |  | 1 |  |  | 200 |  | 0 | 0 | 0 | 200 | 0 | 0 |  |  | 0 | 0 | 0 | 2 | 0 | 0 | [9 empty] | 1925 | 1450 | 250 | 1000 | 650 | 1975 | 7250 |  | 19.25 | 14.5 | 2.5 | 10 | 6.5 | 19.75 | 72.5
2018-04-17 | Finished encoder test bench. | 1 |  |  |  |  | 1 |  | 100 |  | 0 | 0 | 0 | 0 | 100 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | [9 empty] | 1925 | 1450 | 250 | 1000 | 750 | 1975 | 7350 |  | 19.25 | 14.5 | 2.5 | 10 | 7.5 | 19.75 | 73.5
2018-04-17 | LED Integration and function | 2 |  |  | 1 |  |  |  | 200 |  | 0 | 0 | 200 | 0 | 0 | 0 |  |  | 0 | 0 | 2 | 0 | 0 | 0 | [9 empty] | 1925 | 1450 | 450 | 1000 | 750 | 1975 | 7550 |  | 19.25 | 14.5 | 4.5 | 10 | 7.5 | 19.75 | 75.5
2018-04-17 | Led VHDL | 2 |  |  | 1 |  |  |  | 200 |  | 0 | 0 | 200 | 0 | 0 | 0 |  |  | 0 | 0 | 2 | 0 | 0 | 0 | [9 empty] | 1925 | 1450 | 650 | 1000 | 750 | 1975 | 7750 |  | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 19.75 | 77.5
2018-04-17 | Verify C function, wrapper, and functional test logic | 2 | [5 empty] | 1 | 200 |  | 0 | 0 | 0 | 0 | 0 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 2 | [9 empty] | 1925 | 1450 | 650 | 1000 | 750 | 2175 | 7950 |  | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 21.75 | 79.5
2018-04-18 | Refactored C and python wrapper functions | 1 | [5 empty] | 1 | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | [9 empty] | 1925 | 1450 | 650 | 1000 | 750 | 2275 | 8050 |  | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 22.75 | 80.5
2018-04-18 | Adjusted C offsets, tested wk 13 blink axi on rover | 1.5 | [5 empty] | 1 | 150 |  | 0 | 0 | 0 | 0 | 0 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 1.5 | [9 empty] | 1925 | 1450 | 650 | 1000 | 750 | 2425 | 8200 |  | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 24.25 | 82
2018-04-18 | Documented diagrams of functional tests and web interface | 0.25 | [5 empty] | 1 | 25 |  | 0 | 0 | 0 | 0 | 0 | 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0.25 | [9 empty] | 1925 | 1450 | 650 | 1000 | 750 | 2450 | 8225 |  | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 82.25
2018-04-18 | Reorganized Dashboard | 1.5 | 1 | [5 empty] | 150 |  | 150 | 0 | 0 | 0 | 0 | 0 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
2018-04-19 | Completed encoder tech memo. | 1.5 |  |  |  |  | 1 |  | 150 |  | 0 | 0 | 0 | 0 | 150 | 0 |  |  | 0 | 0 | 0 | 0 | 1.5 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Total CDR Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | Total CDR Costs | [8 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28 | [8 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
[9 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 20.75 | 14.5 | 6.5 | 10 | 9 | 24.5 | 85.25
| Total | 72.75 | 19.25 | 14.5 | 4.5 | 10 | 6.5 | 24.5 | 8525 | Total | 2075 | 1450 | 650 | 1000 | 900 | 2450 | 8525 |  | 19.25 | 14.5 | 4.5 | 10 | 6.5 | 24.5 | 79.25
|  | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost