## Burn Report
Per Person
Date | Task | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost
2018-02-04 | [Ignore] For Chart Formatting | 0 | [6 empty] | 0
2018-02-06 | Meeting Planning | 0.5 | 1 | [5 empty] | 50
2018-02-13 | Meeting Planning | 0.5 | 1 | [5 empty] | 50
2018-02-22 | Derive Requirements for Motor | 2 |  | 1 | 1 | 1 |  |  | 600
2018-02-22 | Derive Requirements for Motor | 1 |  | 1 |  |  |  |  | 100
2018-02-22 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  | 1 | 200
2018-02-22 | Gather hardware manuals along with examples for hardware implementations | 2 |  | 1 |  |  |  |  | 200
2018-02-24 | Block diagram for whole system | 1 |  |  |  |  | 1 |  | 100
2018-02-26 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100
2018-02-26 | Came up with requirements for system and modules | 1 |  | 1 |  |  |  |  | 100
2018-02-27 | Derive Requirements for sensors | 0.5 |  | 1 |  |  | 1 |  | 100
2018-02-27 | Wrote a summary and requirement report for ultrasonic sensors | 2 |  | 1 |  |  |  |  | 200
2018-02-28 | Create a block diagram for PWM | 0.5 |  |  | 1 |  |  |  | 50
2018-02-28 | Python Motor idea implementation | 0.5 |  |  |  | 1 |  |  | 50
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | [5 empty] | 1 | 50
2018-03-01 | Finish up task list, updated burn list, and started gantt | 1.5 | 1 | [5 empty] | 150
2018-03-01 | Python Sensor idea implementation | 1 | [5 empty] | 1 | 100
2018-03-05 | Explore opencv object detection | 1 | [5 empty] | 1 | 100
2018-03-06 | Create and train Haar cascades for various ‘brick’ faces | 2 | [5 empty] | 1 | 200
2018-03-06 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100
2018-03-06 | Created initial revision of pre-pdr gantt | 1 | 1 |  |  |  |  | 1 | 200
2018-03-07 | Retrain cascades with new samples – shell script automation | 0.5 | [5 empty] | 1 | 50
2018-03-07 | Worked on Gantt and organizing files | 1 | 1 | [5 empty] | 100
2018-03-08 | Came up with test plan for system and modules | 1 |  | 1 |  |  |  |  | 100
2018-03-13 | Design GUI and brainstorm ideas for functionality | 2 |  |  |  | 1 |  |  | 200
2018-03-13 | Organized Files in folders | 0.25 | 1 | [5 empty] | 25
2018-03-14 | Further Organized and Updated Gantt | 1 | 1 | [5 empty] | 100
2018-03-14 | Researched OpenCV functionality with python | 0.5 | [5 empty] | 1 | 50
2018-03-15 | Worked on Powerpoint and Gantt. Communicated with team | 1 | 1 | [5 empty] | 100
2018-03-17 | Brainstormed project's application and purpose | 0.5 | 1 | [5 empty] | 50
2018-03-18 | Created Powerpoint skeleton and updated Gantt. | 1 | 1 | [5 empty] | 100
2018-03-20 | Designed VHDL block dragrams for sensor modules. | 1.5 |  |  |  |  | 1 |  | 150
2018-03-20 | Wrote VHDL for sensor modules. | 2.5 |  |  |  |  | 1 |  | 250
2018-03-20 | Added OpenCV and python module to PDR | 1 | [5 empty] | 1 | 100
2018-03-21 | Cleaned up Burn Report and added intro into slides | 1.5 | 1 | [5 empty] | 150
2018-03-21 | Drove to fire station and interviewed with firemen to get ideas on how to help them | 1 | 1 | [5 empty] | 100
2018-03-21 | Added requirements for the system as a whole and for each subsystem to PDR | 3 |  | 1 |  |  |  |  | 300
2018-03-21 | Added hardware overview and test plan to PDR | 2 |  | 1 |  |  |  |  | 200
2018-03-21 | Worked on PP | 1 | 1 | [5 empty] | 100
2018-03-22 | Finalized PP | 1 | 1 | [5 empty] | 100
2018-03-24 | Researched localization and other algorithms | 3 | [5 empty] | 1 | 300
2018-03-26 | Created Individual Gantt Charts for each team member | 2 | 1 | [5 empty] | 200
2018-03-27 | Created basic Memory Access Unit tests in Python and C | 0.5 | [5 empty] | 1 | 50
2018-03-28 | Added more metrics to our Planner and combined reports/created dashboard for flexibility | 1 | 1 | [5 empty] | 100
2018-04-02 | Messing around with dashboard and charts | 1.5 | 1 | [5 empty] | 150
2018-04-04 | Experimenting creation of time card | 1 | 1 | [5 empty] | 100
2018-04-06 | Remapped Python GUI memory and verified functionality | 0.5 |  |  |  | 1 |  |  | 50
2018-04-09 | Wrote functional test for Professor’s system | 1 | [5 empty] | 1 | 100
2018-04-09 | Researched OpenCV and developed camera calibration script | 1.5 | [5 empty] | 1 | 150
2018-04-10 | Cleaned up Metrics, polished up burn reports & discarding time card | 1 | 1 | [5 empty] | 100
2018-04-10 | Wrote VHDL for encoder reader and counter. | 1 |  |  |  |  | 1 |  | 100
2018-04-11 | Familiarize/tweak IMU and wrote script integrating turn and IMU | 1.5 | [5 empty] | 1 | 150
2018-04-14 | Finished sensor python/c unit/integration test | 1 | [5 empty] | 1 | 100
2018-04-16 | Wrote C memory poking for motors | 0.5 | [5 empty] | 1 | 50
2018-04-16 | Modularized all components in python with shared object use | 0.5 | [5 empty] | 1 | 50
2018-04-16 | Wrote functional test including sensor, imu and motor components | 1 | [5 empty] | 1 | 100
2018-04-17 | Begun initial work on web interface of rover with straight, left, right, backward, and 360 buttons | 0.75 | [5 empty] | 1 | 75
2018-04-17 | GUI - Movement Map | 2 |  |  |  | 1 |  |  | 200
2018-04-17 | Finished encoder test bench. | 1 |  |  |  |  | 1 |  | 100
2018-04-17 | LED Integration and function | 2 |  |  | 1 |  |  |  | 200
2018-04-17 | Led VHDL | 2 |  |  | 1 |  |  |  | 200
2018-04-17 | Verify C function, wrapper, and functional test logic | 2 | [5 empty] | 1 | 200
2018-04-18 | Refactored C and python wrapper functions | 1 | [5 empty] | 1 | 100
2018-04-18 | Adjusted C offsets, tested wk 13 blink axi on rover | 1.5 | [5 empty] | 1 | 150
2018-04-18 | Documented diagrams of functional tests and web interface | 0.25 | [5 empty] | 1 | 25
2018-04-18 | Reorganized Dashboard | 1.5 | 1 | [5 empty] | 150
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[9 empty] | 0 | W
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total | 72.75 | 19.25 | 14.5 | 4.5 | 10 | 6.5 | 24.5 | 8375
|  | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost

## Meeting Costs
Per Person
Date | Notes | Hours | Andrei | Bach | Brandon | Cody | Peter | Zach | Cost
2018-02-01 |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-06 |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-08 |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-13 |  | 0.75 | 1 |  | 1 | 1 | 1 | 1 | 375
2018-02-20 | Overview + Subsystems | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600
2018-02-22 | Motor Requirements | 1 |  | 1 | 1 | 1 | 1 | 1 | 500
2018-02-27 | Sensor Requirements | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 900
2018-03-01 | Powerpoint, encoders, | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1200
2018-03-05 | PDR discussion | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-03-06 | Project Plan Review & obj for spring break | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600
2018-03-08 | obj for spring break | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-03-20 | Update status, prepare Powerpoint, go over PDR | 2 | 1 |  | 1 | 1 | 1 | 1 | 1000
2018-03-27 | Lessons learned PDR & demoed new gantt system | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-04-05 | Assigned Tasks and talked about what is needed for following week | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600
2018-04-10 | Reviewed what was completed, what the next tasks needed. Demo'd changes | 0.75 | 1 | 1 | 1 | 1 | 1 | 1 | 450
2018-04-12 |  | 0.5 | 1 |  | 1 | 1 | 1 | 1 | 250
0
0
0
0
0
0
| Total | 14.5 | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5 | 8275
|  | Hours | Andrei | Bach | Brandon | Cody | Peter | Zach | Cost

## Total Metrics
Tasks
| Andrei | Bach | Brandon | Cody | Peter | Zack
Pre PDR Cost | 1275 | 1450 | 250 | 750 | 550 | 850
Post PDR Cost | 800 | 0 | 400 | 250 | 200 | 1600
Pre PDR Hours | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5
Post PDR Hours | 6.5 | 0 | 2 | 2.5 | 1 | 16
Total Cost | 2075 | 1450 | 650 | 1000 | 750 | 2450
Total Hours | 19.25 | 14.5 | 4.5 | 10 | 6.5 | 24.5
Meeting
| Andrei | Bach | Brandon | Cody | Peter | Zack
Pre PDR Costs | 1075 | 900 | 1175 | 1175 | 1175 | 1175
Post PDR Costs | 275 | 225 | 275 | 275 | 275 | 275
Pre PDR Hours | 10.75 | 9 | 11.75 | 11.75 | 11.75 | 11.75
Post PDR Hours | 2.75 | 2.25 | 2.75 | 2.75 | 2.75 | 2.75
Total Costs | 1350 | 1125 | 1450 | 1450 | 1450 | 1450
Total Hours | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5

## Task Metrics
Cumulative
Individual Costs | [7 empty] | Individual Time Spent | [7 empty] | Individual Costs | [7 empty] | Individual Time Spent
| Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack | Team |  | Andrei | Bach | Brandon | Cody | Peter | Zack | Team
2018-02-06 | 50 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-06 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-06 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 2018-02-06 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5
2018-02-13 | 50 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-13 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-02-13 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-02-13 | 1 | 0 | 0 | 0 | 0 | 0 | 1
2018-02-22 | 0 | 200 | 200 | 200 | 0 | 0 |  | 2018-02-22 | 0 | 2 | 2 | 2 | 0 | 0 |  | 2018-02-22 | 100 | 200 | 200 | 200 | 0 | 0 | 700 | 2018-02-22 | 1 | 2 | 2 | 2 | 0 | 0 | 7
2018-02-22 | 0 | 100 | 0 | 0 | 0 | 0 |  | 2018-02-22 | 0 | 1 | 0 | 0 | 0 | 0 |  | 2018-02-22 | 100 | 300 | 200 | 200 | 0 | 0 | 800 | 2018-02-22 | 1 | 3 | 2 | 2 | 0 | 0 | 8
2018-02-22 | 0 | 0 | 0 | 100 | 0 | 100 |  | 2018-02-22 | 0 | 0 | 0 | 1 | 0 | 1 |  | 2018-02-22 | 100 | 300 | 200 | 300 | 0 | 100 | 1000 | 2018-02-22 | 1 | 3 | 2 | 3 | 0 | 1 | 10
2018-02-22 | 0 | 200 | 0 | 0 | 0 | 0 |  | 2018-02-22 | 0 | 2 | 0 | 0 | 0 | 0 |  | 2018-02-22 | 100 | 500 | 200 | 300 | 0 | 100 | 1200 | 2018-02-22 | 1 | 5 | 2 | 3 | 0 | 1 | 12
2018-02-24 | 0 | 0 | 0 | 0 | 100 | 0 |  | 2018-02-24 | 0 | 0 | 0 | 0 | 1 | 0 |  | 2018-02-24 | 100 | 500 | 200 | 300 | 100 | 100 | 1300 | 2018-02-24 | 1 | 5 | 2 | 3 | 1 | 1 | 13
2018-02-26 | 0 | 0 | 0 | 100 | 0 | 0 |  | 2018-02-26 | 0 | 0 | 0 | 1 | 0 | 0 |  | 2018-02-26 | 100 | 500 | 200 | 400 | 100 | 100 | 1400 | 2018-02-26 | 1 | 5 | 2 | 4 | 1 | 1 | 14
2018-02-26 | 0 | 100 | 0 | 0 | 0 | 0 |  | 2018-02-26 | 0 | 1 | 0 | 0 | 0 | 0 |  | 2018-02-26 | 100 | 600 | 200 | 400 | 100 | 100 | 1500 | 2018-02-26 | 1 | 6 | 2 | 4 | 1 | 1 | 15
2018-02-27 | 0 | 50 | 0 | 0 | 50 | 0 |  | 2018-02-27 | 0 | 0.5 | 0 | 0 | 0.5 | 0 |  | 2018-02-27 | 100 | 650 | 200 | 400 | 150 | 100 | 1600 | 2018-02-27 | 1 | 6.5 | 2 | 4 | 1.5 | 1 | 16
2018-02-27 | 0 | 200 | 0 | 0 | 0 | 0 |  | 2018-02-27 | 0 | 2 | 0 | 0 | 0 | 0 |  | 2018-02-27 | 100 | 850 | 200 | 400 | 150 | 100 | 1800 | 2018-02-27 | 1 | 8.5 | 2 | 4 | 1.5 | 1 | 18
2018-02-28 | 0 | 0 | 50 | 0 | 0 | 0 |  | 2018-02-28 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 2018-02-28 | 100 | 850 | 250 | 400 | 150 | 100 | 1850 | 2018-02-28 | 1 | 8.5 | 2.5 | 4 | 1.5 | 1 | 18.5
2018-02-28 | 0 | 0 | 0 | 50 | 0 | 0 |  | 2018-02-28 | 0 | 0 | 0 | 0.5 | 0 | 0 |  | 2018-02-28 | 100 | 850 | 250 | 450 | 150 | 100 | 1900 | 2018-02-28 | 1 | 8.5 | 2.5 | 4.5 | 1.5 | 1 | 19
2018-02-28 | 0 | 0 | 0 | 0 | 0 | 50 |  | 2018-02-28 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 2018-02-28 | 100 | 850 | 250 | 450 | 150 | 150 | 1950 | 2018-02-28 | 1 | 8.5 | 2.5 | 4.5 | 1.5 | 1.5 | 19.5
2018-03-01 | 150 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-01 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-01 | 250 | 850 | 250 | 450 | 150 | 150 | 2100 | 2018-03-01 | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 1.5 | 21
2018-03-01 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-03-01 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-03-01 | 250 | 850 | 250 | 450 | 150 | 250 | 2200 | 2018-03-01 | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 2.5 | 22
2018-03-05 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-03-05 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-03-05 | 250 | 850 | 250 | 450 | 150 | 350 | 2300 | 2018-03-05 | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 3.5 | 23
2018-03-06 | 0 | 0 | 0 | 0 | 0 | 200 |  | 2018-03-06 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2018-03-06 | 250 | 850 | 250 | 450 | 150 | 550 | 2500 | 2018-03-06 | 2.5 | 8.5 | 2.5 | 4.5 | 1.5 | 5.5 | 25
2018-03-06 | 0 | 0 | 0 | 100 | 0 | 0 |  | 2018-03-06 | 0 | 0 | 0 | 1 | 0 | 0 |  | 2018-03-06 | 250 | 850 | 250 | 550 | 150 | 550 | 2600 | 2018-03-06 | 2.5 | 8.5 | 2.5 | 5.5 | 1.5 | 5.5 | 26
2018-03-06 | 100 | 0 | 0 | 0 | 0 | 100 |  | 2018-03-06 | 1 | 0 | 0 | 0 | 0 | 1 |  | 2018-03-06 | 350 | 850 | 250 | 550 | 150 | 650 | 2800 | 2018-03-06 | 3.5 | 8.5 | 2.5 | 5.5 | 1.5 | 6.5 | 28
2018-03-07 | 0 | 0 | 0 | 0 | 0 | 50 |  | 2018-03-07 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 2018-03-07 | 350 | 850 | 250 | 550 | 150 | 700 | 2850 | 2018-03-07 | 3.5 | 8.5 | 2.5 | 5.5 | 1.5 | 7 | 28.5
2018-03-07 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-07 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-07 | 450 | 850 | 250 | 550 | 150 | 700 | 2950 | 2018-03-07 | 4.5 | 8.5 | 2.5 | 5.5 | 1.5 | 7 | 29.5
2018-03-08 | 0 | 100 | 0 | 0 | 0 | 0 |  | 2018-03-08 | 0 | 1 | 0 | 0 | 0 | 0 |  | 2018-03-08 | 450 | 950 | 250 | 550 | 150 | 700 | 3050 | 2018-03-08 | 4.5 | 9.5 | 2.5 | 5.5 | 1.5 | 7 | 30.5
2018-03-13 | 0 | 0 | 0 | 200 | 0 | 0 |  | 2018-03-13 | 0 | 0 | 0 | 2 | 0 | 0 |  | 2018-03-13 | 450 | 950 | 250 | 750 | 150 | 700 | 3250 | 2018-03-13 | 4.5 | 9.5 | 2.5 | 7.5 | 1.5 | 7 | 32.5
2018-03-13 | 25 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-13 | 0.25 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-13 | 475 | 950 | 250 | 750 | 150 | 700 | 3275 | 2018-03-13 | 4.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7 | 32.75
2018-03-14 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-14 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-14 | 575 | 950 | 250 | 750 | 150 | 700 | 3375 | 2018-03-14 | 5.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7 | 33.75
2018-03-14 | 0 | 0 | 0 | 0 | 0 | 50 |  | 2018-03-14 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 2018-03-14 | 575 | 950 | 250 | 750 | 150 | 750 | 3425 | 2018-03-14 | 5.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 34.25
2018-03-15 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-15 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-15 | 675 | 950 | 250 | 750 | 150 | 750 | 3525 | 2018-03-15 | 6.75 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 35.25
2018-03-17 | 50 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-17 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-17 | 725 | 950 | 250 | 750 | 150 | 750 | 3575 | 2018-03-17 | 7.25 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 35.75
2018-03-18 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-18 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-18 | 825 | 950 | 250 | 750 | 150 | 750 | 3675 | 2018-03-18 | 8.25 | 9.5 | 2.5 | 7.5 | 1.5 | 7.5 | 36.75
2018-03-20 | 0 | 0 | 0 | 0 | 150 | 0 |  | 2018-03-20 | 0 | 0 | 0 | 0 | 1.5 | 0 |  | 2018-03-20 | 825 | 950 | 250 | 750 | 300 | 750 | 3825 | 2018-03-20 | 8.25 | 9.5 | 2.5 | 7.5 | 3 | 7.5 | 38.25
2018-03-20 | 0 | 0 | 0 | 0 | 250 | 0 |  | 2018-03-20 | 0 | 0 | 0 | 0 | 2.5 | 0 |  | 2018-03-20 | 825 | 950 | 250 | 750 | 550 | 750 | 4075 | 2018-03-20 | 8.25 | 9.5 | 2.5 | 7.5 | 5.5 | 7.5 | 40.75
2018-03-20 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-03-20 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-03-20 | 825 | 950 | 250 | 750 | 550 | 850 | 4175 | 2018-03-20 | 8.25 | 9.5 | 2.5 | 7.5 | 5.5 | 8.5 | 41.75
2018-03-21 | 150 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 975 | 950 | 250 | 750 | 550 | 850 | 4325 | 2018-03-21 | 9.75 | 9.5 | 2.5 | 7.5 | 5.5 | 8.5 | 43.25
2018-03-21 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1075 | 950 | 250 | 750 | 550 | 850 | 4425 | 2018-03-21 | 10.75 | 9.5 | 2.5 | 7.5 | 5.5 | 8.5 | 44.25
2018-03-21 | 0 | 300 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 0 | 3 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1075 | 1250 | 250 | 750 | 550 | 850 | 4725 | 2018-03-21 | 10.75 | 12.5 | 2.5 | 7.5 | 5.5 | 8.5 | 47.25
2018-03-21 | 0 | 200 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 0 | 2 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1075 | 1450 | 250 | 750 | 550 | 850 | 4925 | 2018-03-21 | 10.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 | 49.25
2018-03-21 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-21 | 1175 | 1450 | 250 | 750 | 550 | 850 | 5025 | 2018-03-21 | 11.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 | 50.25
2018-03-22 | 100 | 0 | 0 | 0 | 0 | 0 | Total PDR Costs | 2018-03-22 | 1 | 0 | 0 | 0 | 0 | 0 | Total PDR hours | 2018-03-22 | 1275 | 1450 | 250 | 750 | 550 | 850 | 5125 | 2018-03-22 | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 8.5 | 51.25
2018-03-24 | 0 | 0 | 0 | 0 | 0 | 300 | 5125 | 2018-03-24 | 0 | 0 | 0 | 0 | 0 | 3 | 51.25 | 2018-03-24 | 1275 | 1450 | 250 | 750 | 550 | 1150 | 5425 | 2018-03-24 | 12.75 | 14.5 | 2.5 | 7.5 | 5.5 | 11.5 | 54.25
2018-03-26 | 200 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-26 | 2 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-26 | 1475 | 1450 | 250 | 750 | 550 | 1150 | 5625 | 2018-03-26 | 14.75 | 14.5 | 2.5 | 7.5 | 5.5 | 11.5 | 56.25
2018-03-27 | 0 | 0 | 0 | 0 | 0 | 50 |  | 2018-03-27 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 2018-03-27 | 1475 | 1450 | 250 | 750 | 550 | 1200 | 5675 | 2018-03-27 | 14.75 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 56.75
2018-03-28 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-28 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-03-28 | 1575 | 1450 | 250 | 750 | 550 | 1200 | 5775 | 2018-03-28 | 15.75 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 57.75
2018-04-02 | 150 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-02 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-02 | 1725 | 1450 | 250 | 750 | 550 | 1200 | 5925 | 2018-04-02 | 17.25 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 59.25
2018-04-04 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-04 | 1825 | 1450 | 250 | 750 | 550 | 1200 | 6025 | 2018-04-04 | 18.25 | 14.5 | 2.5 | 7.5 | 5.5 | 12 | 60.25
2018-04-06 | 0 | 0 | 0 | 50 | 0 | 0 |  | 2018-04-06 | 0 | 0 | 0 | 0.5 | 0 | 0 |  | 2018-04-06 | 1825 | 1450 | 250 | 800 | 550 | 1200 | 6075 | 2018-04-06 | 18.25 | 14.5 | 2.5 | 8 | 5.5 | 12 | 60.75
2018-04-09 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-04-09 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-04-09 | 1825 | 1450 | 250 | 800 | 550 | 1300 | 6175 | 2018-04-09 | 18.25 | 14.5 | 2.5 | 8 | 5.5 | 13 | 61.75
2018-04-09 | 0 | 0 | 0 | 0 | 0 | 150 |  | 2018-04-09 | 0 | 0 | 0 | 0 | 0 | 1.5 |  | 2018-04-09 | 1825 | 1450 | 250 | 800 | 550 | 1450 | 6325 | 2018-04-09 | 18.25 | 14.5 | 2.5 | 8 | 5.5 | 14.5 | 63.25
2018-04-10 | 100 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-10 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-10 | 1925 | 1450 | 250 | 800 | 550 | 1450 | 6425 | 2018-04-10 | 19.25 | 14.5 | 2.5 | 8 | 5.5 | 14.5 | 64.25
2018-04-10 | 0 | 0 | 0 | 0 | 100 | 0 |  | 2018-04-10 | 0 | 0 | 0 | 0 | 1 | 0 |  | 2018-04-10 | 1925 | 1450 | 250 | 800 | 650 | 1450 | 6525 | 2018-04-10 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 14.5 | 65.25
2018-04-11 | 0 | 0 | 0 | 0 | 0 | 150 |  | 2018-04-11 | 0 | 0 | 0 | 0 | 0 | 1.5 |  | 2018-04-11 | 1925 | 1450 | 250 | 800 | 650 | 1600 | 6675 | 2018-04-11 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 16 | 66.75
2018-04-14 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-04-14 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-04-14 | 1925 | 1450 | 250 | 800 | 650 | 1700 | 6775 | 2018-04-14 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 17 | 67.75
2018-04-16 | 0 | 0 | 0 | 0 | 0 | 50 |  | 2018-04-16 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 2018-04-16 | 1925 | 1450 | 250 | 800 | 650 | 1750 | 6825 | 2018-04-16 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 17.5 | 68.25
2018-04-16 | 0 | 0 | 0 | 0 | 0 | 50 |  | 2018-04-16 | 0 | 0 | 0 | 0 | 0 | 0.5 |  | 2018-04-16 | 1925 | 1450 | 250 | 800 | 650 | 1800 | 6875 | 2018-04-16 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 18 | 68.75
2018-04-16 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-04-16 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-04-16 | 1925 | 1450 | 250 | 800 | 650 | 1900 | 6975 | 2018-04-16 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 19 | 69.75
2018-04-17 | 0 | 0 | 0 | 0 | 0 | 75 |  | 2018-04-17 | 0 | 0 | 0 | 0 | 0 | 0.75 |  | 2018-04-17 | 1925 | 1450 | 250 | 800 | 650 | 1975 | 7050 | 2018-04-17 | 19.25 | 14.5 | 2.5 | 8 | 6.5 | 19.75 | 70.5
2018-04-17 | 0 | 0 | 0 | 200 | 0 | 0 |  | 2018-04-17 | 0 | 0 | 0 | 2 | 0 | 0 |  | 2018-04-17 | 1925 | 1450 | 250 | 1000 | 650 | 1975 | 7250 | 2018-04-17 | 19.25 | 14.5 | 2.5 | 10 | 6.5 | 19.75 | 72.5
2018-04-17 | 0 | 0 | 0 | 0 | 100 | 0 |  | 2018-04-17 | 0 | 0 | 0 | 0 | 1 | 0 |  | 2018-04-17 | 1925 | 1450 | 250 | 1000 | 750 | 1975 | 7350 | 2018-04-17 | 19.25 | 14.5 | 2.5 | 10 | 7.5 | 19.75 | 73.5
2018-04-17 | 0 | 0 | 200 | 0 | 0 | 0 |  | 2018-04-17 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2018-04-17 | 1925 | 1450 | 450 | 1000 | 750 | 1975 | 7550 | 2018-04-17 | 19.25 | 14.5 | 4.5 | 10 | 7.5 | 19.75 | 75.5
2018-04-17 | 0 | 0 | 200 | 0 | 0 | 0 |  | 2018-04-17 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2018-04-17 | 1925 | 1450 | 650 | 1000 | 750 | 1975 | 7750 | 2018-04-17 | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 19.75 | 77.5
2018-04-17 | 0 | 0 | 0 | 0 | 0 | 200 |  | 2018-04-17 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2018-04-17 | 1925 | 1450 | 650 | 1000 | 750 | 2175 | 7950 | 2018-04-17 | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 21.75 | 79.5
2018-04-18 | 0 | 0 | 0 | 0 | 0 | 100 |  | 2018-04-18 | 0 | 0 | 0 | 0 | 0 | 1 |  | 2018-04-18 | 1925 | 1450 | 650 | 1000 | 750 | 2275 | 8050 | 2018-04-18 | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 22.75 | 80.5
2018-04-18 | 0 | 0 | 0 | 0 | 0 | 150 |  | 2018-04-18 | 0 | 0 | 0 | 0 | 0 | 1.5 |  | 2018-04-18 | 1925 | 1450 | 650 | 1000 | 750 | 2425 | 8200 | 2018-04-18 | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 24.25 | 82
2018-04-18 | 0 | 0 | 0 | 0 | 0 | 25 |  | 2018-04-18 | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 2018-04-18 | 1925 | 1450 | 650 | 1000 | 750 | 2450 | 8225 | 2018-04-18 | 19.25 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 82.25
2018-04-18 | 150 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-18 | 1.5 | 0 | 0 | 0 | 0 | 0 |  | 2018-04-18 | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 | 2018-04-18 | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 | Total CDR Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | Total CDR Costs |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 | 3250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28 |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 20.75 | 14.5 | 6.5 | 10 | 7.5 | 24.5 | 83.75
Total | 2075 | 1450 | 650 | 1000 | 750 | 2450 | 8375 |  | 19.25 | 14.5 | 4.5 | 10 | 6.5 | 24.5 | 79.25

## Meeting Metrics
Cumulative
Individual Costs | [7 empty] | Individual Time Spent | [7 empty] | Individual Costs | [7 empty] | Individual Time Spent
| Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack |  |  | Andrei | Bach | Brandon | Cody | Peter | Zack | Team |  | Andrei | Bach | Brandon | Cody | Peter | Zack
2018-02-01 | 50 | 50 | 50 | 50 | 50 | 50 |  | 2018-02-01 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-02-01 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-02-01 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
2018-02-06 | 50 | 50 | 50 | 50 | 50 | 50 |  | 2018-02-06 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-02-06 | 100 | 100 | 100 | 100 | 100 | 100 | 900 | 2018-02-06 | 1 | 1 | 1 | 1 | 1 | 1
2018-02-08 | 50 | 50 | 50 | 50 | 50 | 50 |  | 2018-02-08 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-02-08 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 2018-02-08 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2018-02-13 | 75 | 0 | 75 | 75 | 75 | 75 |  | 2018-02-13 | 0.75 | 0 | 0.75 | 0.75 | 0.75 | 0.75 |  | 2018-02-13 | 225 | 150 | 225 | 225 | 225 | 225 | 3075 | 2018-02-13 | 2.25 | 1.5 | 2.25 | 2.25 | 2.25 | 2.25
2018-02-20 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2018-02-20 | 1 | 1 | 1 | 1 | 1 | 1 |  | 2018-02-20 | 325 | 250 | 325 | 325 | 325 | 325 | 4950 | 2018-02-20 | 3.25 | 2.5 | 3.25 | 3.25 | 3.25 | 3.25
2018-02-22 | 0 | 100 | 100 | 100 | 100 | 100 |  | 2018-02-22 | 0 | 1 | 1 | 1 | 1 | 1 |  | 2018-02-22 | 325 | 350 | 425 | 425 | 425 | 425 | 7325 | 2018-02-22 | 3.25 | 3.5 | 4.25 | 4.25 | 4.25 | 4.25
2018-02-27 | 150 | 150 | 150 | 150 | 150 | 150 |  | 2018-02-27 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | 2018-02-27 | 475 | 500 | 575 | 575 | 575 | 575 | 10600 | 2018-02-27 | 4.75 | 5 | 5.75 | 5.75 | 5.75 | 5.75
2018-03-01 | 200 | 200 | 200 | 200 | 200 | 200 |  | 2018-03-01 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2018-03-01 | 675 | 700 | 775 | 775 | 775 | 775 | 15075 | 2018-03-01 | 6.75 | 7 | 7.75 | 7.75 | 7.75 | 7.75
2018-03-05 | 50 | 50 | 50 | 50 | 50 | 50 |  | 2018-03-05 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-03-05 | 725 | 750 | 825 | 825 | 825 | 825 | 19850 | 2018-03-05 | 7.25 | 7.5 | 8.25 | 8.25 | 8.25 | 8.25
2018-03-06 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2018-03-06 | 1 | 1 | 1 | 1 | 1 | 1 |  | 2018-03-06 | 825 | 850 | 925 | 925 | 925 | 925 | 25225 | 2018-03-06 | 8.25 | 8.5 | 9.25 | 9.25 | 9.25 | 9.25
2018-03-08 | 50 | 50 | 50 | 50 | 50 | 50 |  | 2018-03-08 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-03-08 | 875 | 900 | 975 | 975 | 975 | 975 | 30900 | 2018-03-08 | 8.75 | 9 | 9.75 | 9.75 | 9.75 | 9.75
2018-03-20 | 200 | 0 | 200 | 200 | 200 | 200 |  | 2018-03-20 | 2 | 0 | 2 | 2 | 2 | 2 |  | 2018-03-20 | 1075 | 900 | 1175 | 1175 | 1175 | 1175 | 37575 | 2018-03-20 | 10.75 | 9 | 11.75 | 11.75 | 11.75 | 11.75
2018-03-27 | 50 | 50 | 50 | 50 | 50 | 50 |  | 2018-03-27 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-03-27 | 1125 | 950 | 1225 | 1225 | 1225 | 1225 | 44550 | 2018-03-27 | 11.25 | 9.5 | 12.25 | 12.25 | 12.25 | 12.25
2018-04-05 | 100 | 100 | 100 | 100 | 100 | 100 |  | 2018-04-05 | 1 | 1 | 1 | 1 | 1 | 1 |  | 2018-04-05 | 1225 | 1050 | 1325 | 1325 | 1325 | 1325 | 52125 | 2018-04-05 | 12.25 | 10.5 | 13.25 | 13.25 | 13.25 | 13.25
2018-04-10 | 75 | 75 | 75 | 75 | 75 | 75 |  | 2018-04-10 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 |  | 2018-04-10 | 1300 | 1125 | 1400 | 1400 | 1400 | 1400 | 60150 | 2018-04-10 | 13 | 11.25 | 14 | 14 | 14 | 14
2018-04-12 | 50 | 0 | 50 | 50 | 50 | 50 |  | 2018-04-12 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | 0.5 |  | 2018-04-12 | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 68425 | 2018-04-12 | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 76700 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 84975 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 93250 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 101525 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 109800 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
| 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 118075 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5
Total | 1350 | 1125 | 1450 | 1450 | 1450 | 1450 | 8275 |  | 13.5 | 11.25 | 14.5 | 14.5 | 14.5 | 14.5 | 82.75
Formulas:
Individual Costs = IF('Meeting Costs'!$[Individual Costs, row above] = "","",'Meeting Costs'!$[Individual Costs, row above])
Individual Time Spent = IF('Meeting Costs'!$[Individual Costs, row above] = "","",'Meeting Costs'!$[Individual Costs, row above])

## Total Data
Individual Costs | [7 empty] | Cumulative
Date | Andrei | Bach | Brandon | Cody | Peter | Zack | Team | Individual Costs | Andrei | Bach | Brandon | Cody | Peter | Zack | Team
2018-02-01 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-02-01 | 50 | 50 | 50 | 50 | 50 | 50 | 300
2018-02-06 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 2018-02-06 | 100 | 50 | 50 | 50 | 50 | 50 | 350
2018-02-06 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-02-06 | 150 | 100 | 100 | 100 | 100 | 100 | 650
2018-02-08 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-02-08 | 200 | 150 | 150 | 150 | 150 | 150 | 950
2018-02-13 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 2018-02-13 | 250 | 150 | 150 | 150 | 150 | 150 | 1000
2018-02-13 | 75 | 0 | 75 | 75 | 75 | 75 | 375 | 2018-02-13 | 325 | 150 | 225 | 225 | 225 | 225 | 1375
2018-02-20 | 100 | 100 | 100 | 100 | 100 | 100 | 600 | 2018-02-20 | 425 | 250 | 325 | 325 | 325 | 325 | 1975
2018-02-22 | 0 | 200 | 200 | 200 | 0 | 0 | 600 | 2018-02-22 | 425 | 450 | 525 | 525 | 325 | 325 | 2575
2018-02-22 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 2018-02-22 | 425 | 550 | 525 | 525 | 325 | 325 | 2675
2018-02-22 | 0 | 0 | 0 | 100 | 0 | 100 | 200 | 2018-02-22 | 425 | 550 | 525 | 625 | 325 | 425 | 2875
2018-02-22 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 2018-02-22 | 425 | 750 | 525 | 625 | 325 | 425 | 3075
2018-02-22 | 0 | 100 | 100 | 100 | 100 | 100 | 500 | 2018-02-22 | 425 | 850 | 625 | 725 | 425 | 525 | 3575
2018-02-24 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 2018-02-24 | 425 | 850 | 625 | 725 | 525 | 525 | 3675
2018-02-26 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 2018-02-26 | 425 | 850 | 625 | 825 | 525 | 525 | 3775
2018-02-26 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 2018-02-26 | 425 | 950 | 625 | 825 | 525 | 525 | 3875
2018-02-27 | 0 | 50 | 0 | 0 | 50 | 0 | 100 | 2018-02-27 | 425 | 1000 | 625 | 825 | 575 | 525 | 3975
2018-02-27 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 2018-02-27 | 425 | 1200 | 625 | 825 | 575 | 525 | 4175
2018-02-27 | 150 | 150 | 150 | 150 | 150 | 150 | 900 | 2018-02-27 | 575 | 1350 | 775 | 975 | 725 | 675 | 5075
2018-02-28 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 2018-02-28 | 575 | 1350 | 825 | 975 | 725 | 675 | 5125
2018-02-28 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 2018-02-28 | 575 | 1350 | 825 | 1025 | 725 | 675 | 5175
2018-02-28 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2018-02-28 | 575 | 1350 | 825 | 1025 | 725 | 725 | 5225
2018-03-01 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 2018-03-01 | 725 | 1350 | 825 | 1025 | 725 | 725 | 5375
2018-03-01 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-03-01 | 725 | 1350 | 825 | 1025 | 725 | 825 | 5475
2018-03-01 | 200 | 200 | 200 | 200 | 200 | 200 | 1200 | 2018-03-01 | 925 | 1550 | 1025 | 1225 | 925 | 1025 | 6675
2018-03-05 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-03-05 | 925 | 1550 | 1025 | 1225 | 925 | 1125 | 6775
2018-03-05 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-03-05 | 975 | 1600 | 1075 | 1275 | 975 | 1175 | 7075
2018-03-06 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 2018-03-06 | 975 | 1600 | 1075 | 1275 | 975 | 1375 | 7275
2018-03-06 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 2018-03-06 | 975 | 1600 | 1075 | 1375 | 975 | 1375 | 7375
2018-03-06 | 100 | 0 | 0 | 0 | 0 | 100 | 200 | 2018-03-06 | 1075 | 1600 | 1075 | 1375 | 975 | 1475 | 7575
2018-03-06 | 100 | 100 | 100 | 100 | 100 | 100 | 600 | 2018-03-06 | 1175 | 1700 | 1175 | 1475 | 1075 | 1575 | 8175
2018-03-07 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2018-03-07 | 1175 | 1700 | 1175 | 1475 | 1075 | 1625 | 8225
2018-03-07 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-07 | 1275 | 1700 | 1175 | 1475 | 1075 | 1625 | 8325
2018-03-08 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 2018-03-08 | 1275 | 1800 | 1175 | 1475 | 1075 | 1625 | 8425
2018-03-08 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-03-08 | 1325 | 1850 | 1225 | 1525 | 1125 | 1675 | 8725
2018-03-13 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 2018-03-13 | 1325 | 1850 | 1225 | 1725 | 1125 | 1675 | 8925
2018-03-13 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 2018-03-13 | 1350 | 1850 | 1225 | 1725 | 1125 | 1675 | 8950
2018-03-14 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-14 | 1450 | 1850 | 1225 | 1725 | 1125 | 1675 | 9050
2018-03-14 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2018-03-14 | 1450 | 1850 | 1225 | 1725 | 1125 | 1725 | 9100
2018-03-15 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-15 | 1550 | 1850 | 1225 | 1725 | 1125 | 1725 | 9200
2018-03-17 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 2018-03-17 | 1600 | 1850 | 1225 | 1725 | 1125 | 1725 | 9250
2018-03-18 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-18 | 1700 | 1850 | 1225 | 1725 | 1125 | 1725 | 9350
2018-03-20 | 0 | 0 | 0 | 0 | 150 | 0 | 150 | 2018-03-20 | 1700 | 1850 | 1225 | 1725 | 1275 | 1725 | 9500
2018-03-20 | 0 | 0 | 0 | 0 | 250 | 0 | 250 | 2018-03-20 | 1700 | 1850 | 1225 | 1725 | 1525 | 1725 | 9750
2018-03-20 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-03-20 | 1700 | 1850 | 1225 | 1725 | 1525 | 1825 | 9850
2018-03-20 | 200 | 0 | 200 | 200 | 200 | 200 | 1000 | 2018-03-20 | 1900 | 1850 | 1425 | 1925 | 1725 | 2025 | 10850
2018-03-21 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 2018-03-21 | 2050 | 1850 | 1425 | 1925 | 1725 | 2025 | 11000
2018-03-21 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-21 | 2150 | 1850 | 1425 | 1925 | 1725 | 2025 | 11100
2018-03-21 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 2018-03-21 | 2150 | 2150 | 1425 | 1925 | 1725 | 2025 | 11400
2018-03-21 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 2018-03-21 | 2150 | 2350 | 1425 | 1925 | 1725 | 2025 | 11600
2018-03-21 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-21 | 2250 | 2350 | 1425 | 1925 | 1725 | 2025 | 11700
2018-03-22 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-22 | 2350 | 2350 | 1425 | 1925 | 1725 | 2025 | 11800
2018-03-24 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 2018-03-24 | 2350 | 2350 | 1425 | 1925 | 1725 | 2325 | 12100
2018-03-26 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 2018-03-26 | 2550 | 2350 | 1425 | 1925 | 1725 | 2325 | 12300
2018-03-27 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2018-03-27 | 2550 | 2350 | 1425 | 1925 | 1725 | 2375 | 12350
2018-03-27 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2018-03-27 | 2600 | 2400 | 1475 | 1975 | 1775 | 2425 | 12650
2018-03-28 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-03-28 | 2700 | 2400 | 1475 | 1975 | 1775 | 2425 | 12750
2018-04-02 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 2018-04-02 | 2850 | 2400 | 1475 | 1975 | 1775 | 2425 | 12900
2018-04-04 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-04-04 | 2950 | 2400 | 1475 | 1975 | 1775 | 2425 | 13000
2018-04-05 | 100 | 100 | 100 | 100 | 100 | 100 | 600 | 2018-04-05 | 3050 | 2500 | 1575 | 2075 | 1875 | 2525 | 13600
2018-04-06 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 2018-04-06 | 3050 | 2500 | 1575 | 2125 | 1875 | 2525 | 13650
2018-04-09 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-04-09 | 3050 | 2500 | 1575 | 2125 | 1875 | 2625 | 13750
2018-04-09 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 2018-04-09 | 3050 | 2500 | 1575 | 2125 | 1875 | 2775 | 13900
2018-04-10 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 2018-04-10 | 3150 | 2500 | 1575 | 2125 | 1875 | 2775 | 14000
2018-04-10 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 2018-04-10 | 3150 | 2500 | 1575 | 2125 | 1975 | 2775 | 14100
2018-04-10 | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 2018-04-10 | 3225 | 2575 | 1650 | 2200 | 2050 | 2850 | 14550
2018-04-11 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 2018-04-11 | 3225 | 2575 | 1650 | 2200 | 2050 | 3000 | 14700
2018-04-12 | 50 | 0 | 50 | 50 | 50 | 50 | 250 | 2018-04-12 | 3275 | 2575 | 1700 | 2250 | 2100 | 3050 | 14950
2018-04-14 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-04-14 | 3275 | 2575 | 1700 | 2250 | 2100 | 3150 | 15050
2018-04-16 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2018-04-16 | 3275 | 2575 | 1700 | 2250 | 2100 | 3200 | 15100
2018-04-16 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2018-04-16 | 3275 | 2575 | 1700 | 2250 | 2100 | 3250 | 15150
2018-04-16 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-04-16 | 3275 | 2575 | 1700 | 2250 | 2100 | 3350 | 15250
2018-04-17 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 2018-04-17 | 3275 | 2575 | 1700 | 2250 | 2100 | 3425 | 15325
2018-04-17 | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 2018-04-17 | 3275 | 2575 | 1700 | 2450 | 2100 | 3425 | 15525
2018-04-17 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 2018-04-17 | 3275 | 2575 | 1700 | 2450 | 2200 | 3425 | 15625
2018-04-17 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 2018-04-17 | 3275 | 2575 | 1900 | 2450 | 2200 | 3425 | 15825
2018-04-17 | 0 | 0 | 200 | 0 | 0 | 0 | 200 | 2018-04-17 | 3275 | 2575 | 2100 | 2450 | 2200 | 3425 | 16025
2018-04-17 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 2018-04-17 | 3275 | 2575 | 2100 | 2450 | 2200 | 3625 | 16225
2018-04-18 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2018-04-18 | 3275 | 2575 | 2100 | 2450 | 2200 | 3725 | 16325
2018-04-18 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 2018-04-18 | 3275 | 2575 | 2100 | 2450 | 2200 | 3875 | 16475
2018-04-18 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 2018-04-18 | 3275 | 2575 | 2100 | 2450 | 2200 | 3900 | 16500
2018-04-18 | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 2018-04-18 | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3425 | 2575 | 2100 | 2450 | 2200 | 3900 | 16650
Formulas:
Individual Costs = IF([Date]="","",[Date])