## Risk Report
Type of Risk | Risk | Risk Probablity | Risk Level | Risk Extra Cost | Risk Extra Duration | Follow up plan | Legend
Hardware | Battery Dies | Med | Low |  |  | Charge battery when the battery is 30% or lower | Types of Risks |  | Risk Level
Hardware | Battery Fries | Low | Critial |  | 2+ Days | Speak to teacher | Functionality | Causes system to not function as required | Low | Will not destroy functionality
Hardware | Battery Charger stops working | Low | High |  | 2+ Days | Speak to teacher and barrow battery charger | Bug | Creates a minor issue | Med | Creates intermittent issues or unknowns
Hardware | Snickerdoodle Fries | Low | Critial |  | 2+ Days | Speak to teacher |  |  | High | Creates an issue to a large part of system
Hardware | Motors burn out | Low | Critial |  | 2+ Days | Speak to teacher | Question | Poses a question of not unknown | Crit | Breaks System
Hardware | Motor gears are damaged | Low | Critial |  | 2+ Days | Speak to teacher
Hardware | Cameras are not available | Med | Low | 1000 | 2 | Create a plan that doesn't use cameras
Hardware | Sensor doesn't function | Low | Critial |  | 2+ Days | Speak to teacher
Hardware | Serial Cable not working | Low | Med |  |  | We can swap it out
Environment | Different floors | High | Med |  |  | Create coeffients to handle different surfaces and/or test with other surfaces
Software | Losing Data | Med | Med |  |  | Backup data more often
System | Software & Hardware Imcompability
Software | IMU giving poor data
Hardware | Motors connected in reverse