## Burn Report
Task Date | Task Title | Hours | Bodies | Unit Cost | Total Task Cost | Worker
2018-02-06 | Initial Consulting | 0.5 | 5 | 100 | 250
2018-02-08 |  |  |  |  | 0
2018-02-13 | Task Planning | 0.5 | 6 | 100 | 300
2018-02-22 | Derive Requirements for Motor | 2 | 4 | 100 | 800
2018-02-22 | Derive Requirements for sensors |  |  |  | 0
| Design movement opcodes\algorithm |  |  |  | 0
| Design final PWM VHDL\AXI subsystem |  |  |  | 0
| Implement PWM final design |  |  |  | 0
| Design python GUI program for basic movement |  |  |  | 0
| Python IMU functions (gyro) |  |  |  | 0
| Make turning smart with gyro |  |  |  | 0
| Design VHDL\AXI block for sonic sensors |  |  |  | 0
| Write VHDL for sonic sensors |  |  |  | 0
| Read sonic sensors in python program |  |  |  | 0
| Calibration - VHDL side |  |  |  | 0
| Calibration - python side |  |  |  | 0
| Powerpoint |  |  |  | 0
| Block diagram for whole system |  | 1 |  | 0
2018-02-28 | Python Motor design (pseudo code/examples/diagrams) | 0.5 | 1 | 100 | 50 | C & Z
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | 1 | 100 | 50 | Zack

## Tasks
ESD II Final Project Tasks
Task ID | Task Title | Hrs | Priority | Risk | Worker | Status
1.1 | System design | 1 | 1 | 3 |  | In Progress
1.2 | Identify requirements | 0 | 1 | 1 |  | ToDo
1.3 | Set up Schedule and Requirements | 3 | 3 | 1 | Andrei | In Progress
1.4 | Research PWM & Encoders | 1 | 1 | 1 | Peter | In Progress
1.5 | Research PWM & Encoders | 1 | 1 | 1 | Brandon | In Progress
1.6 | Research Python | 1 | 1 | 1 | Cody | In Progress
1.7 | Research Linux | 1 | 1 | 1 | Zach | In Progress
1.8 | Research PCB | 1 | 1 | 1 | Bach | In Progress
1.9 | Research Project Ultrasonic sensor | 1 | 1 | 1 | Andrei | In Progress
1.10 | Derive Requirements for Motor |  | 3 |  | Bach | In Progress
1.11 | Derive Requirements for sensors |  | 3 |  | Bach | In Progress
1.12 | Design movement opcodes\algorithm |  | 3 |  | Bach | To Do
1.13 | Design final PWM VHDL\AXI subsystem |  | 3 |  | B & P | In Progress
1.14 | Implement PWM final design |  | 2 |  | B & P | To Do
1.15 | Design python GUI program for basic movement |  | 2 |  | C & Z | To Do
1.16 | Python IMU functions (gyro) |  | 1 |  | C & Z | To Do
1.17 | Make turning smart with gyro |  | 1 |  | C & Z | To Do
1.18 | Design VHDL\AXI block for sonic sensors |  | 3 |  | B & P | To Do
1.19 | Write VHDL for sonic sensors |  | 2 |  | B & P | To Do
1.20 | Read sonic sensors in python program |  | 1 |  | C & Z | To Do
1.21 | Calibration - VHDL side |  | 1 |  | B & P | To Do
1.22 | Calibration - python side |  | 1 |  | C & Z | To Do
1.23 | Powerpoint |  | 3 |  | Andrei | To Do
1.24 | Block diagram for whole system |  | 3 |  | Team | In Progress
| Scheduling post-pdr |  | 2 |  | Andrei