## Leads and Support
newFolder
|  | Lead | Support |  | Lead | Support
Peter Lodato | pxl3892 | VHDL Driver Development For MPU9250 | C Driver Development For MPU9250 | Project Managerment | Andrei | Cody
Brandon Brown | blb1084 | VHDL Driver Development For MPU9250 | C Driver Development For MPU9250 | VHDL | Peter & Brandon
Andrei Fusilli | amf9934 | Project Management | Audio Engineering | C Development | Peter & Brandon
Cody Guay | cag1632 | Python Development | Project Management | Python | Cody
Zachary Weeden | zdw7287 | Linux Driver Development | OpenCV Development | Linux Driver | Zach
Bach Nguyen | bdn9867 | PCB Design | Requirements Management | Requirements | Bach
|  |  |  | OpenCV | Zach
|  |  |  | Audio Engineering | Andrei
|  |  |  | PCB | Bach

## Weekly Meetings Costs
Date | Hours | Andrei | Bach | Brandon | Cody | Peter | Zach | Task Cost | Notes | Unit Cost | 100
2018-02-01 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-06 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-08 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-13 | 0.75 | 1 | 0 | 1 | 1 | 1 | 1 | 375
2018-02-20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600 | Overview + Subsystems
2018-02-22 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 500 | Motor Requirements
2018-02-27 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 900 | Sensor Requirements
2018-03-01 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1200 | Powerpoint, encoders,
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| 7.75 | [6 empty] | 4475 | Total

## Burn Report (2)
Date | Task | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost | Unit Cost | 100
2018-02-06 | Meeting Planning | 0.5 | 1 | [5 empty] | 50
2018-02-13 | Meeting Planning | 0.5 | 1 | [5 empty] | 50
2018-03-01 | Finish up task list, updated burn list, and started gantt | 1.5 | [6 empty] | 0
2018-02-24 | Block diagram for whole system | 1 | [6 empty] | 0
2018-02-22 | Derive Requirements for Motor | 2 | 0 | 1 | 1 | 1 | 0 | 1 | 800
2018-02-22 | Derive Requirements for Motor | 1 |  | 1 |  |  |  |  | 100
2018-02-27 | Derive Requirements for sensors | [7 empty] | 0
2018-02-22 | Design GUI and brainstorm ideas for functionality |  |  |  |  | 1 |  |  | 0
2018-02-26 | Design GUI and brainstorm ideas for functionality |  |  |  |  | 1 |  |  | 0
2018-02-28 | Create a block diagram for PWM |  |  |  | 1 |  |  |  | 0
2018-02-28 | Python Motor design (pseudo code/examples/diagrams) | 0.5 |  |  |  | 1 |  | 1 | 100
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | [5 empty] | 1 | 50
0
0
0
0
0
0
0
0
0
1150

## Tasks
ESD II Final Project Tasks
Task ID | Task Title | Hrs | Priority | Risk | Worker | Status | Task ID | Task Subject | Task Title | Hrs | Priority | Risk | Worker | Status
1.1 |  | 1 | 1 | 3 | Andrei | In Progress | 1.1 | Project Management | Create logging sheets for easy reports |  | 3 | 1 | Andrei | In Progress
1.2 |  | 0 | 1 | 1 |  | ToDo | 1.2 |  | Scheduling pre PDR |  | 3 |  | Andrei | In Progress
1.3 |  | 3 | 3 | 1 | Andrei | In Progress | 1.3 |  | Scheduling post PDR |  | 2 |  | Andrei | To Do
1.4 | Research PWM & Encoders | 1 | 1 | 1 | Peter | In Progress | 1.4 |  | Create Powerpoint |  | 3 |  | Andrei | To Do
1.5 | Research PWM & Encoders | 1 | 1 | 1 | Brandon | In Progress | 1.5 |  | Practice PDR |  | 1 |  | Team | To Do
1.6 | Research Python | 1 | 1 | 1 | Cody | In Progress | 1.6
1.7 | Research Linux | 1 | 1 | 1 | Zach | In Progress | 1.7
1.8 | Research PCB | 1 | 1 | 1 | Bach | In Progress |  | VHDL
1.9 | Research Project Ultrasonic sensor | 1 | 1 | 1 | Andrei | In Progress | 2.1 |  | Derive Requirements for VHDL |  | 3 |  | Bach | In Progress
1.10 | [6 empty] | 2.2 |  | Create a block diagram for PWM |  |  |  | B & P
1.11 | [6 empty] | 2.3 |  | Design VHDL\AXI block for PWM | 1 | 3 | 1 | Brandon | Completed
1.12 | Design movement opcodes\algorithm |  | 3 |  | Bach | To Do | 2.4 |  | Design VHDL\AXI block for sonic sensors |  | 3 |  | B & P | To Do
1.13 | [6 empty] | 2.5 |  | Create AXI on Vivado
1.14 | [6 empty] | 2.6 |  | Write VHDL for sonic sensors |  | 2 |  | B & P | To Do
1.15 | [6 empty] | 2.7 |  | Calibration - VHDL side |  | 1 |  | B & P | To Do
1.16 | [8 empty] | Implement PWM final design |  | 2 |  | B & P | To Do
1.17 | [6 empty] | 3.1 | Python | Design GUI and brainstorm ideas for functionality |  |  |  | C & Z
1.18 | [6 empty] | 3.2 |  | Figure out software requirements |  |  |  | C & Z & Bach
1.19 | [6 empty] | 3.3 |  | Plan what types of functions for movement |  | 2 |  | C & Z | To Do
1.20 | [6 empty] | 3.4 |  | Plan how to process encoders |  |  |  | C & Z
1.21 | [6 empty] | 3.5 |  | Python IMU functions (gyro) |  | 1 |  | C & Z | To Do
1.22 | [6 empty] | 3.6 |  | Make turning smart with gyro |  | 1 |  | C & Z | To Do
1.23 | [6 empty] | 3.7 |  | Plan a way to calibrate rover |  |  |  | C & Z
[7 empty] | 3.8 |  | Design final PWM VHDL\AXI subsystem |  | 3 |  | B & P | In Progress
[7 empty] | 4.1 | C | Design a process on Polling & Interrupt |  | 2 |  | B & P
[7 empty] | 4.2 |  | Write code to read sonic sensors |  | 1 |  | B & P | To Do
[7 empty] | 4.3 |  | Code up sonic sensors calibration |  | 1 |  | B & P | To Do
[7 empty] | 5.1 | Hardware | Devire Requirements for Motor |  | 3 |  | Bach | In Progress
[7 empty] | 5.2 |  | Devire Requirements for IMU |  | 3 |  | Bach | In Progress
[7 empty] | 5.3 |  | Devire Requirements for LED |  | 3 |  | Bach | In Progress
[7 empty] | 5.4 |  | Devire Requirements for Ultrasonic Sensors |  | 3 |  | Bach | In Progress
[7 empty] | 5.5 |  | Devire Requirements for Audio Speaker |  | 1 |  | Bach | In Progress
[8 empty] | System | Create overview system design | 1.5 | 1 | 3 | Team | In Progress
[9 empty] | Block diagram for whole system |  | 3 | 3 | Team | In Progress
System Requirements
Mechanical Drawings
Sensor Trade Study (choice of sensors)
Create functional test
Develop Tech Memos
Define Technical Deliverables