## Project Planner
New folder Project Planner
2018-03-06 19:09 | [5 empty] | Period Highlight: | 6 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | USER | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS | [30 empty] | April
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
System |  | 1 | 13 | 0 | 0 | 0%
Create overview system design | Team | 1 | 6 | 1 | 0 | 0%
Block diagram for whole system | Team | 1 | 8 | 0 | 0 | 0%
System Requirements | Bach & Team | 1 | 8 | 0 | 0 | 0%
Mechanical Drawings | Bach | 6 | 13 | 0 | 0 | 0%
Sensor Trade Study* (choice of sensors) | Team & Bach | 1 | 6 | 0 | 0 | 0%
Create functional test* |  | 13 | 5 | 0 | 0 | 0%
VHDL - PWM (Duty Cycle) |  | 13 | 5 | 0 | 0 | 0%
Python - Encoders & PWM | Cody | 13 | 5
C - Polling & Interrupts |  | 13 | 0 | 0 | 0 | 0%
VHDL - Ultrasonic Sensors |  | 13 | 0 | 0 | 0 | 0%
Develop Tech Memo* | Team | 13 | 6 | 0 | 0 | 0%
PWM? |  | 13 | 6 | 0 | 0 | 0%
Python - TBD |  | 13 | 6
Rover? | Andrei | 13 | 6 | 0 | 0 | 0%
Define Technical Deliverables* | Andrei | 8 | 13 | 0 | 0 | 0%
VHDL |  | 1 | 8 | 0 | 0 | 0%
Derive Requirements for VHDL | Bach | 1 | 6 | 0 | 0 | 0%
Create a block diagram for PWM | Brandon & Peter | 1 | 6 | 0 | 0 | 0%
Design VHDL\AXI block for PWM | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Design VHDL\AXI block for sonic sensors | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Register Mapping | Brandon & Peter | 1 | 8
Python |  | 1 | 8 | 0 | 0 | 0%
Figure out software requirements | Cody & Zack & Bach | 1 | 8 | 0 | 0 | 0%
Design GUI and brainstorm ideas for functionality | Cody & Zack | 1 | 8 | 0 | 0 | 0%
Plan what types of functions for movement | Cody & Zack | 1 | 6 | 0 | 0 | 0%
Plan how to process encoders | Cody & Zack | 1 | 8 | 0 | 0 | 0%
Python IMU functions (gyro) | Cody & Zack | 1 | 6 | 0 | 0 | 0%
How to implement calibration system
C Development |  | 1 | 8 | 0 | 0 | 0%
Register Mapping | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Design a process on Polling & Interrupt | Brandon & Peter | 1 | 8 | 0 | 0 | 0%
Plan function names for the drivers | Brandon & Peter | 1 | 6 | 1 | 6 | 100%
Hardware |  | 1 | 8 | 0 | 0 | 0%
Derive Requirements for Motor | Bach | 1 | 8 | 0 | 4 | 0%
Derive Requirements for IMU | Bach | 6 | 8 | 0 | 0 | 0%
Derive Requirements for LED | Bach | 6 | 8 | 0 | 0 | 0%
Derive Requirements for Ultrasonic Sensors | Bach | 1 | 6 | 1 | 4 | 0%
Derive Requirements for Audio Speaker* | Andrei & Bach | 6 | 2 | 0 | 0 | 0%
Derive Requirements for Cameras | Bach | 8
Plan a way to calibrate rover | Cody & Zack | 1 | 8 | 1 | 0 | 50%
Project Management |  | 1 | 22 | 0 | 0 | 0%
Create logging sheets for easy reports | Andrei | 1 | 6 | 1 | 6 | 50%
Scheduling pre PDR | Andrei | 1 | 8 | 1 | 0 | 75%
Scheduling post PDR | Andrei | 8 | 2 | 0 | 0 | 0%
Create Powerpoint | Andrei & Cody | 4 | 14 | 6 | 0 | 0%
Practice PDR | Team | 18 | 5 | 0 | 0 | 0%
PDR | Team | 22 | 1 | 22 | 1 | 0%
VHDL |  | 22 | 0 | 0 | 0 | 0%
Create AXI on Vivado |  | 22 | 0 | 0 | 0 | 0%
Write VHDL for sonic sensors | B & P | 22 | 0 | 0 | 0 | 0%
Calibration - VHDL side | B & P | 22 | 0 | 0 | 0 | 0%
Implement PWM final design | B & P | 22 | 0 | 0 | 0 | 0%
Python |  | 22 | 0 | 0 | 0 | 0%
Make turning smart with gyro | Cody & Zack | 0 | 0 | 0 | 0 | 0%
C Development |  | 22 | 0 | 0 | 0 | 0%
Write code to read sonic sensors | Brandon & Peter | 0 | 0 | 0 | 0 | 0%
Code up sonic sensors calibration | Brandon & Peter | 0 | 0 | 0 | 0 | 0%

## Leads and Support
newFolder
|  | Lead | Support |  | Lead | Support
Peter Lodato | pxl3892 | VHDL Driver Development For MPU9250 | C Driver Development For MPU9250 | Project Management | Andrei | Cody
Brandon Brown | blb1084 | VHDL Driver Development For MPU9250 | C Driver Development For MPU9250 | VHDL | Peter & Brandon
Andrei Fusilli | amf9934 | Project Management | Audio Engineering | C Development | Peter & Brandon
Cody Guay | cag1632 | Python Development | Project Management | Python | Cody | Zach
Zachary Weeden | zdw7287 | Linux Driver Development | OpenCV Development | Linux Driver | Zach
Bach Nguyen | bdn9867 | PCB Design | Requirements Management | Requirements | Bach
|  |  |  | OpenCV | Zach
|  |  |  | Audio Engineering | Andrei
|  |  |  | PCB | Bach

## Weekly Meetings Costs
Date | Hours | Andrei | Bach | Brandon | Cody | Peter | Zach | Task Cost | Notes | Unit Cost | 100
2018-02-01 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-06 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-08 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2018-02-13 | 0.75 | 1 | 0 | 1 | 1 | 1 | 1 | 375
2018-02-20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 600 | Overview + Subsystems
2018-02-22 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 500 | Motor Requirements
2018-02-27 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 900 | Sensor Requirements
2018-03-01 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1200 | Powerpoint, encoders,
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| 7.75 | [6 empty] | 4475 | Total

## Burn Report
Date | Task | Hours | Andrei | Bach | Brandon | Cody | Peter | Zack | Task Cost | Unit Cost | 100
2018-02-06 | Meeting Planning | 0.5 | 1 | [5 empty] | 50
2018-02-13 | Meeting Planning | 0.5 | 1 | [5 empty] | 50
2018-03-01 | Finish up task list, updated burn list, and started gantt | 1.5 | [6 empty] | 0
2018-02-24 | Block diagram for whole system | 1 | [6 empty] | 0
2018-02-22 | Derive Requirements for Motor | 2 | 0 | 1 | 1 | 1 | 0 | 1 | 800
2018-02-22 | Derive Requirements for Motor | 1 |  | 1 |  |  |  |  | 100
2018-02-27 | Derive Requirements for sensors | [7 empty] | 0
2018-02-22 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100
2018-02-26 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100
2018-02-28 | Create a block diagram for PWM |  |  |  | 1 |  |  |  | 0
2018-02-28 | Python Motor idea implementation | 0.5 |  |  |  | 1 |  | 1 | 100
2018-02-28 | Wrapped memory access logic in class – modularization | 0.5 | [5 empty] | 1 | 50
2018-03-01 | Python Sensor idea implementation | 1 | [5 empty] | 1 | 100
2018-03-05 | Explore opencv object detection | 1 | [5 empty] | 1 | 100
2018-03-06 | Create and Train haar cascades for various ‘brick’ faces | 2 | [5 empty] | 1 | 200
2018-03-06 | Design GUI and brainstorm ideas for functionality | 1 |  |  |  | 1 |  |  | 100
0
0
0
0
0
1850

## Tasks
ESD II Final Project Tasks
Task ID | Task Title | Hrs | Priority | Risk | Worker | Status | Task ID | Task Subject | Task Title | Hrs | Priority | Risk | Worker | Status
1.1 |  | 1 | 1 | 3 | Andrei | In Progress | 1.1 | Project Management | Create logging sheets for easy reports |  | 3 | 1 | Andrei | In Progress
1.2 |  | 0 | 1 | 1 |  | ToDo | 1.2 |  | Scheduling pre PDR |  | 3 |  | Andrei | In Progress
1.3 |  | 3 | 3 | 1 | Andrei | In Progress | 1.3 |  | Scheduling post PDR |  | 2 |  | Andrei | To Do
1.4 | Research PWM & Encoders | 1 | 1 | 1 | Peter | In Progress | 1.4 |  | Create Powerpoint |  | 3 |  | Andrei | To Do
1.5 | Research PWM & Encoders | 1 | 1 | 1 | Brandon | In Progress | 1.5 |  | Practice PDR |  | 1 |  | Team | To Do
1.6 | Research Python | 1 | 1 | 1 | Cody | In Progress | 1.6
1.7 | Research Linux | 1 | 1 | 1 | Zach | In Progress | 1.7
1.8 | Research PCB | 1 | 1 | 1 | Bach | In Progress |  | VHDL
1.9 | Research Project Ultrasonic sensor | 1 | 1 | 1 | Andrei | In Progress | 2.1 |  | Derive Requirements for VHDL |  | 3 |  | Bach | In Progress
1.10 | [6 empty] | 2.2 |  | Create a block diagram for PWM |  |  |  | B & P
1.11 | [6 empty] | 2.3 |  | Design VHDL\AXI block for PWM | 1 | 3 | 1 | Brandon | Completed
1.12 | Design movement opcodes\algorithm |  | 3 |  | Bach | To Do | 2.4 |  | Design VHDL\AXI block for sonic sensors |  | 3 |  | B & P | To Do
1.13 | [6 empty] | 2.5 |  | Create AXI on Vivado
1.14 | [6 empty] | 2.6 |  | Write VHDL for sonic sensors |  | 2 |  | B & P | To Do
1.15 | [6 empty] | 2.7 |  | Calibration - VHDL side |  | 1 |  | B & P | To Do
1.16 | [8 empty] | Implement PWM final design |  | 2 |  | B & P | To Do
1.17 | [6 empty] | 3.1 | Python | Design GUI and brainstorm ideas for functionality |  |  |  | C & Z
1.18 | [6 empty] | 3.2 |  | Figure out software requirements |  |  |  | C & Z & Bach
1.19 | [6 empty] | 3.3 |  | Plan what types of functions for movement |  | 2 |  | C & Z | To Do
1.20 | [6 empty] | 3.4 |  | Plan how to process encoders |  |  |  | C & Z
1.21 | [6 empty] | 3.5 |  | Python IMU functions (gyro) |  | 1 |  | C & Z | To Do
1.22 | [6 empty] | 3.6 |  | Make turning smart with gyro |  | 1 |  | C & Z | To Do
1.23 | [6 empty] | 3.7 |  | Plan a way to calibrate rover |  |  |  | C & Z
[7 empty] | 3.8 |  | Design final PWM VHDL\AXI subsystem |  | 3 |  | B & P | In Progress
[7 empty] | 4.1 | C | Design a process on Polling & Interrupt |  | 2 |  | B & P
[7 empty] | 4.2 |  | Write code to read sonic sensors |  | 1 |  | B & P | To Do
[7 empty] | 4.3 |  | Code up sonic sensors calibration |  | 1 |  | B & P | To Do
[7 empty] | 5.1 | Hardware | Devire Requirements for Motor |  | 3 |  | Bach | In Progress
[7 empty] | 5.2 |  | Devire Requirements for IMU |  | 3 |  | Bach | In Progress
[7 empty] | 5.3 |  | Devire Requirements for LED |  | 3 |  | Bach | In Progress
[7 empty] | 5.4 |  | Devire Requirements for Ultrasonic Sensors |  | 3 |  | Bach | In Progress
[7 empty] | 5.5 |  | Devire Requirements for Audio Speaker |  | 1 |  | Bach | In Progress
[8 empty] | System | Create overview system design | 1.5 | 1 | 3 | Team | In Progress
[9 empty] | Block diagram for whole system |  | 3 | 3 | Team | In Progress
System Requirements
Mechanical Drawings
Sensor Trade Study (choice of sensors)
Create functional test
Develop Tech Memos
Define Technical Deliverables