## Project Planner
New Folder Project Planner
2018-03-22 15:26 | [5 empty] | Period Highlight: | 22 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | USER | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS | [30 empty] | April
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
System
Create overview system design | Team | 1 | 6 | 1 | 14 | 100%
Block diagram for whole system | Team | 1 | 8 | 8 | 2 | 100%
System Requirements | Bach | 1 | 8 | 6 | 3 | 100%
Mechanical Drawings | Bach | 6 | 13 | 20 | 0 | 50%
Sensor Trade Study* (choice of sensors) | Team & Bach | 1 | 6 | 4 | 2 | 100%
Design functional test* | Team | 13 | 5 | 13 | 1 | 100%
VHDL - PWM (Duty Cycle) | Peter & Brandon | 13 | 5 | 13 | 1 | 100%
Python - Encoders | Cody | 13 | 5 | 13 | 1 | 100%
VHDL & C - Interrupts | Peter & Brandon | 13 | 5 | 13 | 1 | 100%
VHDL
Derive Requirements for VHDL | Bach | 1 | 6 | 1 | 1 | 100%
Create a block diagram for PWM | Brandon & Peter | 1 | 6 | 6 | 2 | 100%
Design VHDL\AXI block for PWM | Brandon & Peter | 1 | 8 | 6 | 2 | 100%
Design VHDL\AXI block for sonic sensors | Brandon & Peter | 1 | 8 | 6 | 2 | 100%
Design block for sonic sensors | Brandon & Peter | 1 | 8 | 6 | 8 | 100%
Register Mapping | Brandon & Peter | 1 | 8 | 12 | 0 | 50%
Python
Figure out software requirements | Cody & Zack & Bach | 1 | 8 | 4 | 3 | 100%
Design GUI and brainstorm ideas for functionality | Cody & Zack | 1 | 8 | 1 | 7 | 100%
Plan what types of functions for movement | Cody & Zack | 1 | 6 | 1 | 3 | 100%
Plan how to process encoders | Cody & Zack | 1 | 8 | 1 | 3 | 100%
Python IMU functions (gyro) | Cody & Zack | 1 | 6 | 14 | 2 | 100%
Plan calibration implementation | Cody & Zack | 1 | 6 | 1 | 2 | 100%
C Development
Register Mapping | Brandon & Peter | 1 | 8 | 12 | 0 | 50%
Design a process on Polling & Interrupt | Brandon & Peter | 1 | 8 | 15 | 3 | 100%
Plan function names for the drivers | Brandon & Peter | 1 | 6 | 1 | 6 | 100%
Hardware
Derive Requirements for Motor | Bach | 1 | 8 | 6 | 4 | 75%
Derive Requirements for IMU | Bach | 6 | 8 | 1 | 8 | 75%
Derive Requirements for Ultrasonic Sensors | Bach | 1 | 6 | 1 | 4 | 100%
Derive Requirements for Cameras | Bach & Zack | 8 | 6 | 14 | 5 | 100%
Plan a way to calibrate rover | Cody & Zack | 1 | 8 | 1 | 10 | 75%
Project Management
Create logging sheets for easy reports | Andrei | 1 | 6 | 1 | 6 | 100%
Think of purpose & application | Andrei | 12 | 7 | 14 | 7 | 100%
Scheduling pre PDR | Andrei | 1 | 8 | 1 | 20 | 100%
Scheduling post PDR | Andrei | 8 | 2 | 11 | 10 | 75%
Create Powerpoint | Andrei & Cody | 4 | 14 | 6 | 15 | 100%
Practice PDR | Team | 18 | 5 | 20 | 2 | 100%
PDR | Team | 22 | 1 | 22 | 1 | 75% | bar: PERIODS 1 to PERIODS 20
System
Create functional test | P & Br & C | 23 | 0 | 0 | 0 | 0%
VHDL - PWM (Duty Cycle) | Peter & Brandon | 23 | 1 | 0 | 0 | 0%
Python - Encoders | Cody | 23 | 1 | 0 | 0 | 0%
VHDL & C - Interrupts | Peter & Brandon | 23 | 2 | 0 | 0 | 0%
Create functional Unit tests | Bach | 23 | 5 | 0 | 0 | 0%
GUI mapping | Bach | 23 | 5 | 0 | 0 | 0%
Sensors | Bach | 23 | 7 | 0 | 0 | 0%
Motors | Bach | 23 | 7 | 0 | 0 | 0%
Calibration | Bach | 31 | 7 | 0 | 0 | 0%
Python | Bach & Cody | 31 | 7 | 0 | 0 | 0%
Ultra sonic sensors | Bach & Br & P | 31 | 7 | 0 | 0 | 0%
VHDL
Create PWM AXI on Vivado | Br & P | 25 | 7 | 0 | 0 | 0%
Create Ultrasonic sensor AXI on Vivado | Br & P | 25 | 7 | 0 | 0 | 0%
Write VHDL for sonic sensors | Br & P | 25 | 10 | 0 | 0 | 0%
Calibration - VHDL side | Br & P | 25 | 10 | 0 | 0 | 0%
Implement PWM final design | Br & P | 25 | 20 | 0 | 0 | 0%
Python
Create GUI | Cody | 23 | 10 | 0 | 0 | 0%
Create camera feed | Zack | 23 | 10 | 0 | 0 | 0%
Create unknown map | Cody | 32 | 15 | 0 | 0 | 0%
Create movement functions | Zack | 32 | 5 | 0 | 0 | 0%
Implement Calibration process | Cody & Zack | 32 | 7 | 0 | 0 | 0%
Make turning smart with gyro | Cody & Zack | 35 | 5 | 0 | 0 | 0%
C Development
Unit Test for writing to memory | Brandon, Peter & Zack | 29 | 3 | 0 | 0 | 0%
Write code to read sonic sensors | Brandon & Peter | 29 | 7 | 0 | 0 | 0%
Project Management
Develop Tech Memo | Team | 41 | 6 | 0 | 0 | 0%
PWM? | ? | 41 | 6 | 0 | 0 | 0%
Python | ? | 41 | 6 | 0 | 0
Rover? | Andrei | 41 | 6 | 0 | 0 | 0%
CDR | Team | 47 | 1 | 47 | 1 | 0%
After We Finish
Create sound board* | Cody & Andrei | TBA | TBA | 0 | 0 | 0%
Implement Wireless Speaker | Andrei | TBA | TBA | 0 | 0 | 0%

## Sheet1
TASK | User | Estimated Time | Estimated Cost
System
Create functional test | P & Br & C |  | 0
VHDL - PWM (Duty Cycle) | Peter & Brandon | 2 | 200
Python - Encoders | Cody | 1 | 100
VHDL & C - Interrupts | Peter & Brandon | 2 | 200
Create functional Unit tests | Bach |  | 0
GUI mapping | Bach | 1 | 100
Sensors | Bach | 2 | 200
Motors | Bach | 1.5 | 150
Calibration | Bach |  | 0
Python | Bach & Cody | 4 | 400
Ultra sonic sensors | Bach & Br & P | 3 | 300
VHDL |  |  | 0
Create PWM AXI on Vivado | Br & P | 2 | 200
Create Ultrasonic sensor AXI on Vivado | Br & P | 2 | 200
Write VHDL for sonic sensors | Br & P | 1.5 | 150
Calibration - VHDL side | Br & P | 2 | 200
Implement PWM final design | Br & P | 3 | 300
Python |  |  | 0
Create GUI | Cody | 3 | 300
Create camera feed | Zack | 2 | 200
Create unknown map | Cody | 3 | 300
Create movement functions | Zack | 2 | 200
Implement Calibration process | Cody & Zack | 1.5 | 150
Make turning smart with gyro | Cody & Zack | 2 | 200
C Development |  |  | 0
Unit Test for writing to memory | Brandon, Peter & Zack | 1 | 100
Write code to read sonic sensors | Brandon & Peter | 1 | 100
Creating Hardware APIs | Brandon & Peter | 3 | 300
Project Management |  |  | 0
Develop Tech Memo | Team |  | 0
PWM? | ? | 1.5 | 150
Python | ? | 1.5 | 150
Rover? | Andrei | 1.5 | 150
|  | 50 | 5000 | Total